# Operation Sukuma Sakhe: Lessons in Managing across Organizational Boundaries

Shanil Haricharan

1. Graduate School of Development Policy and Practice, University of Cape Town, South Africa, 7700 
2. Center for West African Studies of University of Electronic Science and Technology of China, Chengdu, P.R.China, 611731
3. Government Technical Advisory Centre (GTAC), Pretoria, South Africa, 0001

Abstract  In April 2011, the KwaZulu-Natal (KZN) Provincial Premier launched Operation Sukuma Sakhe (OSS), in isiZulu for “Stand Up and Build”. The OSS challenges the common frustration of government’s pervasive and entrenched “silo mentality” resulting in weak coordination and collaboration across the public service that severely impact services to vulnerable households. To ameliorate this situation, the OSS has created political and technical governance structures at provincial, district, local and ward levels. At the community level, ward-based War Rooms are the crucial nexus that connects vulnerable households and communities to government services and social partners. Operating from these War Rooms, under the leadership of the Ward Councilor, the fieldworkers are the lifeblood of these War Rooms. This paper will briefly outline the OSS integrated service delivery model and showcase its workings, achievements, constraints and lessons. A good practice War Room in Ward 4 in the Umngeni Local Municipality is presented.

Key words  War Rooms, Integrated service delivery, Vulnerable households, Collaboration, Leadership, Governance, Community participation, Poverty

## 1 Background

### 1.1 A vignette on OSS

Phindile Ndlovu, a Community Caregiver (CCG), was doing her home visits in Lidgetton, 16km from Howick, in KwaZulu-Natal, when she discovers three young children – alone, dirty and half naked. They were below the age of 10 years. They looked very hungry and there was no food in the house.

Phindile immediately sent a WhatsApp message to her colleague, Fakazile Nzimande, the Community Development Worker (CDW), based at the Lidgetton Community Hall, who in turn phoned the local Ward 4 Councilor Sithembiso Nkuna. On the same day, Councilor Nkuna and the CDW visited the house.

Councilor Nkuna bought groceries from the local shop so the children could receive their meals. Together with the CDW and CCG, they traced the children’s maternal aunt. They were informed that the children’s mother was staying at her workplace in Nottingham Road, 20kms away.

The Ward Councilor drafted a report and referred the children to a Department of Social Development (DSD) social worker. The children were placed at the Khazimula Children’s Home. Their uncle later took them and they lived with him. The children were returned to their mother, but she passed away tragically in a train accident. Since then the children have been in the care of their aunt.

The CCG and CDW followed up the case and monitored the situation. They assisted the aunt with applications for her Identity Document from the Department of Home Affairs (DHA), so she could apply for child support grants from the South African Social Security Agency (SASSA).

The above case was recorded in 2014 in the casebook of the Ward 4 Operation Sukuma Sakhe (OSS) War Room in Lidgetton and situated in the Umngeni Local Municipality in the uMgungundlovu district in the KwaZulu-Natal province, South Africa.

Since 2012, the Lidgetton War Room led by Councilor Nkuna (the political champion), together with Ndlovu (from the KZN Department of Health – DoH), Nzimande (a Department of Cooperative Governance and Traditional Affairs – COGTA – official) and eight other CCGs and two volunteers, including other provincial departmental officials, and social partners have actively and passionately pursued the noble vision of Operation Sukuma Sakhe: Together with committed leadership, creating sustainable livelihoods, through the provision of integrated services to communities, and promoting a better life for all.

### 1.2 Introduction

The intention of the War Rooms, initiated through the War on Poverty programme by the South African Presidency in February 2008, was to address high levels of poverty, inequality, unemployment and the associated social determinants through community-centric and integrated service delivery, i.e. to address the systemic challenges of weak horizontal and vertical collaboration in the public service.

The purpose of this paper is, firstly, to outline the OSS model, and secondly, to broadly reflect on the challenges and the lessons from the past five years of implementing the integrated, people-centric service delivery model to address poverty. A good practice example of the Ward 4 War Room is presented. This paper starts with a brief contextual background to the KZN province.

The methodology for this paper included literature and document reviews, semi-structured interviews with key resource persons managing the OSS programme, site visits and interviews at War Rooms.

## 1.2.1 Poverty and inequality

KwaZulu-Natal bears the largest burden of poverty: 26.3 percent of the poor South Africans reside in this province; and 42 percent of the provincial population live in poverty (StatsSA, 2011). Compounding and complementing the high level of poverty, KZN carries the country’s largest burden of disease, with the highest rate of HIV infection prevalence among antenatal clinic attendees. Tuberculosis claims the second largest number of lives in this province.

The social ills rife in KZN include crime, drug and substance abuse, and women and child abuse. Studies show that sexually transmitted infections are linked to drug and alcohol abuse, multiple sexual partners and unsafe sex. 75% of young children in this province live in poor households – the second highest rate of child poverty after the Eastern Cape Province with 78% (Children’s Institute & Ilifa Labantwana, 2016).

In light of this situation, the cornerstone of Operation Sukuma Sakhe is the promotion of healthy lifestyles and behaviour change. Such changes are expected to decrease the prevalence of HIV, tuberculosis, teenage pregnancy, substance abuse and women and child abuse. Central to the success of the OSS model, in reducing these social ills, is community participation mediated through War Rooms: the nexus of the KZN government’s integrated service delivery model, together with civil society participation.

The OSS theory of change is founded on behaviour change and the empowerment of the youth and women. As Dr Fikile Ndlovu, Chief Director, Priority Programmes at the KZN Office of the Premier (OTP), responsible for Operation Sukuma Sakhe, explains:

“People must stand up and drive the process. By government providing services and a support system, this allows people to lead, and create partnerships with civil society organizations. Our current structures are not developmental. In areas where OSS works it provides the structures for community participation, and anchored in its own challenges of poverty.”

## 1.2.2 Institutional transformation of the public service

In the mid-1990s, the democratic South African government adopted a set of founding policy frameworks and legislation to fundamentally transform the public service from an Apartheid authoritarian bureaucracy to a democratic, developmental and people-centered one. A key objective of the major South African administrative change initiative was to empower, challenge and motivate senior public service managers to be “leaders, visionaries, initiators and effective communicators and decision-makers, capable of responding pro-actively to the challenges of the change process” (RSA, 1995: 3).

Furthermore, the White Paper on Transforming Public Service Delivery (RSA, 1997), was guided by a set of principles for the public service called the Batho Pele (People First) principles, which was later translated into three key public service beliefs: to care, to serve and to belong. These policy changes were mindful of South Africa’s history of poverty, social exclusion and inequality, and also that the previous public service administration drew heavily on industrial-era scientific management and administrative organizational theory and practice. The latter management models led to the dominance of the machine metaphor of organizations.

These models endure into the 21st century and in the shadow of this metaphor many organizations, such as the democratic South African public service, emerge as (Robledo, 2013: 62)

… hierarchical, control-oriented, bureaucratic, and inflexible. Everything must be carefully planned and mechanized…The main problem with this approach is that it tends to suppress the human side of an organization – individuals are mere cogs in a machine that operates under management control…

Despite the post 1994 public transformation agenda, the “bureaucratic and mechanical mindsets” (Ndlovu, 2013) of public managers persists across the public service, including the KZN provincial government. For example a recent study (Haricharan, 2015) in a South African provincial government showed the negative outcomes of rigid, centralized, overly bureaucratic processes, top-down hierarchical structures and governance systems on public servants and their performance. Rather, these models and practices engender dissonant leadership styles and social exclusion the workplace, with negative impact on fairness, equity, voice, recognition and rewards, consequently impeding teamwork and co-ordination, and further entrenching centralized rank-conscious command and control governance, with limited or no delegated power to lower levels.

The organizational culture in such a context is strongly deontological, i.e. primarily focused on bureaucratic norms, duties, rules and regulations; rather than serving, caring, and belonging (in line with the Batho Pele (People First) ethos of the South African government). This results in a discordant culture: disempowering and demoralizing managers and subordinates, and hindering trust building, innovation, efficiency, agility, motivation, and in so doing delaying decision-making and effective service delivery (Haricharan, 2015). Therefore, in the current uncertain, complex and turbulent public institutional environment, research evidence suggests that the traditional organizational models, still popular in the South African public service, as well as in other countries, are obsolete (Haricharan, 2015).

Moreover, scholarly evidence indicates that the traditional image of government as the top-down bureaucracy is gradually shifting towards the idea of networked governance, and that organizational hierarchy is becoming “less important than inter-organizational relationships defined in multiple manners” (Kellis & Ran 2013: 133).

The OSS has experienced the effects of the institutional environment outlined above, and has challenged the programme’s guiding aim to promote networked governance through integration and co-operation among key government stakeholders in addressing poverty and inequality.

## 2 The journey of Operation Sukuma Sakhe

The OSS journey started in 1994 with the introduction of the democratic government’s pro-poor policies and programmes, which recognized the high levels of poverty and inequality inherited by provinces such as KwaZulu-Natal, comprising a former homeland administration. To achieve the national government’s strategic priority in addressing poverty, the KZN government launched Operation Mbo in 2006 in Msinga and Nkandla, two of the poorest areas. The intention of this Massification Programme was to promote departments working together in a coordinated and integrated manner, together with communities and local government to implement development projects.

In February 2008, KZN’s efforts to address poverty received another strategic boost with the launch of the War on Poverty Programme by former President Thabo Mbeki. The programme targeted the most deprived wards and households, whose needs were profiled. The concept of a ‘War Room on Poverty’ was introduced in the Presidency, and similar structures started to emerge at a local level in KZN.

In 2009, the War on Poverty programme received greater impetus as a provincial Flagship Programme, with the aim of implementing a comprehensive, inclusive, and holistic plan on poverty eradication. The objectives were: 1. Fighting diseases such as HIV and TB, and addressing poverty, 2. Behavior change related to HIV, substance abuse, teenage pregnancy, crime and gender based violence, 3. Empowerment of women and youth. These objectives were to be achieved through five pillars which are community partnerships, behavior change, integration of government services, economic activities and environmental care. At the centre of integration of government services was the drive to profile the poorest households in the most deprived wards, initially in three provincial districts, subsequently spreading to all districts in KZN. Task teams were established to oversee the profiling, referral and monitoring of households. Relevant provincial government departments provided specific interventions to vulnerable households. The Flagship Programme fostered the participation of communities and other social partners in the delivery of services and community development.

Building on these efforts to redress poverty, using a people-centric approach to service delivery and through government’s support to public participation processes, Operation Sukuma Sakhe (isiZulu for Stand up and build) was launched in April 2011. This programme’s aim is to rebuild the fabric of society by promoting human values, fighting poverty, crime, diseases, deprivation and social ills, ensuring moral regeneration and by working together through effective partnerships.

Partnerships include civil society, development partners, communities, and government departments all working together to provide a comprehensive integrated service package to communities.

## 3 The OSS strategic framework and service delivery model

The overall strategic objective of OSS is to integrate, co-ordinate and facilitate transversal services to communities. In response to the persistent cycle of poverty, social ills and the bureaucratic service delivery inefficiencies, and to realize the intent of a ‘better life for all’, the OSS pursued outcomes of healthy lifestyles, sustainable livelihoods, social partnerships, committed leadership, and integrated service delivery. In line with the pro-poor agenda of government, the primary beneficiaries of the OSS are the most vulnerable groups within poor households. These include the elderly, women, children, youth, disabled, working poor, jobless, unskilled and illiterate and the sick.

The implementation of the OSS integrated service delivery model is central to achieving the programme’s desired outcomes (refer to Figure 1). The three key elements of the OSS model are: a) Five critical areas, b) Governance and leadership structures, and c) War Rooms. To address the needs of the most vulnerable groups, five interlinked critical areas, namely community partnerships, behaviour change, integration of government services, economic activities and environmental care, forms the pillars of the Sukuma Sakhe service delivery model.

Community participation is integral to the philosophy of Operation Sukuma Sakhe and for the success of the programme. The War Room in a ward provides an important space to build community partnerships through government departments interfacing with the community on the services they can expect, and the community providing their needs and feedback on public services. At the centre of community participation is the role of community leaders who provide leadership to the community, such as religious leaders and traditional leaders, viz. Amakhosi and Izinduna, civil society leaders and professionals residing in the ward. The political leaders (Councilor), supported by ward committees, champions the approach in the ward; while the Amakhosi with traditional councils champion the approach in areas that falls under traditional councils.

The governance and leadership of OSS is through a matrix of political oversight structures, coordinating task teams, oversight committees and the AIDS councils, at provincial, district, local and ward levels. These structures mostly exist already as political and administrative structures. The OSS structures and oversight mechanisms were intended to provide leadership guidance and direction, and to facilitate cooperation and coordination among stakeholders, across all levels of government in the province. This intention was to give effect to the objective of comprehensive, integrated, transversal services to communities through seamless service delivery.

The Provincial Task Team (PTT) maintains the momentum of Operation Sukuma Sakhe at a provincial level. It is made up of an executive, government departments and strategic Operation Sukuma Sakhe ‘champions’. The overall champion for OSS is the Premier of KwaZulu-Natal. The Premier, MECs and Heads of Departments (HODs) are assigned to each of the eleven districts to play the role of champions from a political and administrative perspective respectively. A provincial level champion (senior official) is appointed as a convener and is charged with supporting the district in gaining buy-in from all stakeholders and to assist in mobilizing resources.

Figure 1 Operation Sukuma Sakhe integrated service delivery model

War Rooms are the intended central nodes from which government services are rendered. Key to the optimal functioning of a War Room and achieving the overall objective of OSS are government departments working at ward, local, district and provincial level to ensure that services are delivered in line with identified community needs. In partnership with government departments, civil society organizations and the private sector also contribute to service delivery, adding another dimension to integrated service delivery through the War Rooms.

Each department is mandated to be involved in the War Room and to render services where they are most needed. Some of the key government departments are Health, Social Development (its agency, the South African Social Security Agency, SASSA), Basic Education, Home Affairs, Agriculture and the South African Police Service. Service delivery also takes place through mobile clinics or scheduled visits by the departments to the War Rooms on set days.

The ‘backbone’ of OSS is community fieldworkers (Community Development Workers, CCGs, Extension Officers, Sport Volunteers, Social Crime Prevention Volunteers), located at a War Room, who are responsible for encouraging social behaviour change through their interaction with household members. The intention is to support vulnerable groups to take responsibility for their sexual behaviour, practice safe sexual conduct, respect the law, prevent crime, prevent violence and live healthy lifestyles.

Through their household visits and profiling, fieldworkers gather important data on the conditions on the ground, and identify common problems and issues in the community, as well as the specific problems that each household faces. The fieldworkers’ job, such as a CCG (belonging to the Department of Health and the Department of Social Development) is not only limited to health or social services issues; they will also look at other issues in the household, such as food insecurity, employment, Identity Documents, basic services whilst educating the household on a range of topics among others.

## 4 OSS good practice: Ward 4 War Room

Those wards that have implemented Operation Sukuma Sakhe in line with the model and objectives have high performing War Rooms. One such is the Ward 4 War Room in Lidgetton, near the town of Escourt.

The Ward 4 War Room team attributes their success to planning, teamwork, leadership, hard work, and passion. The CDW, CCGs, volunteers and Ward Councilor work as a closely-knit team. As the Ward Councilor Sithembiso Nkuna notes: “The War Room team tackle matters hands-on and find solutions.” They meet weekly. The CCGs are proud of their Councilor as he provides exemplary leadership. In the past five years he has built strong relationships with stakeholders and embedded planning and operational systems. As one CCG admired: “He is a hard-worker, kind, and communicates well, and is not fearful to elevate issues to higher levels [within the provincial government].”

At the monthly stakeholder meetings of government and social partners, the CCGs report on their households, follow-up on interventions and closure of cases. Departments report on progress of the referrals from the War Room. An annual schedule of meetings is sent to departments. Once a month, CCGs meet with their counterparts from the other wards in the Umngeni local municipal area as a platform for sharing and receiving updates from their departmental supervisors.

The Ward 4 War Room works with many support organizations, such as Ethembeni, TB/HIV Care Association, Rotary, Red Cross and CareWorks. These organizations, including school principals, attend the monthly War Room meetings. Over the past five years, the Ward Councilor has worked hard to build relationships with social partners, recognizing that, as he says, “Government alone cannot provide services.”

Ward 4 has a Phila Mntwana health facility. A CCG measures the children’s basic growth and health indicators, while urgent cases are referred to the local health clinic. The CCGs work closely with the family health team at the clinic through social media (SMS and Whatsapp). A mobile clinic visits the War Room twice a month. The Ward 4 AIDS Council ensures that people take their medication. The CCGs follow-up on defaulters and check on chronic medication users. Residents find it difficult to get to the clinic as public transport is not readily available or people have no money for the fare. As from March 2016, the introduction of a mediport at the War Room has made it easier for patients to receive their medication rather than to travel to the clinic.

The team proudly lists the many achievements: 50% referrals closed, reduced new infections in TB and HIV, increased awareness within households, better understanding of households, 99% of those eligible receive social grants, attended to and provided services to people living on farms, 21 water tanks distributed, and so on.

Although Ward 4 is a Premier’s Annual Award-winning War Room with many achievements to show over the past five years, the community and the War Room continue to confront several challenges: for example there are too few CCGs, administrative resource deficits, social ills, like drug and alcohol abuse, and a lack of social facilities.

## 5 Discussion

Over the past five years, Operation Sukuma Sakhe has achieved many successes, and also experienced several challenges, in operationalizing the initiative as an integrated, people-centric approach to service delivery to address poverty, inequality and social ills. This section highlights key successes and challenges that the OSS experienced in achieving the overall strategic objective of OSS to integrate, co-ordinate and facilitate transversal services to communities.

### 5.1 Impact of OSS

The ultimate desired outcome of Operation Sukuma Sakhe is the eradication of HIV, poverty and social ills in KZN. To achieve this, the programme set itself intermediate outcomes of committed leadership, sustainable livelihoods and integrated services to communities. The initial focus of the OSS in accomplishing these outcomes was to address the huge socials ills in the province through promoting healthy lifestyles and behaviour change, and secondly to establish War Rooms as the integrating nexus for government services, social partners and communities. Currently, there are 823 War Rooms across the province with a population of approximately 10 million people and 2,5 million households (StasSA, 2011).

As no formal evaluation of the OSS exists, it is difficult to assess the degree to which the programme has achieved the planned outputs or desired outcomes. However, Ndlovu’s study (2013) and the OTP’s five-year review (2015) do provide some insights into the programme’s achievements. The main findings of the study (Ndlovu, 2013) on organizational change factors that impact on the implementation of OSS in KZN were that all change levers were important in driving change. The levers implemented were leadership, strategy, communication/marketing and structure, while the levers of technology, human resource management, budget and quality, were either not implemented or not effectively implemented. The OTP’s review (2015), supported by BroadReach Corporation, tracked 40 households and received insightful feedback and reflections from beneficiaries. The review presents a number of household case studies, narratives, and interviews relating to the programme’s activities, outputs and outcomes.

For example, a Community Caregiver, Thembisile Mdletshe, from Stezi in the Ntambanana Local Municipality, reflected as follows (OTP, 2015):

The child said, “Yes, I am strong” and came over and gave me a big hug and said, “Thank you for the job you do, thank you!” For the mother too, it was the hope I had brought into the house and that is something I learnt from Operation Sukuma Sakhe.

The following narrative from a family in Msinga, one of the poorest areas in South Africa, illustrates the potential of OSS in addressing poverty and development (OTP, 2015):

In 2008, 17 of us children, ranging from 2 to 22 years of age, lived with our grandmother in a one-bedroom mud shack in Msinga. It was initially three bedrooms before parts of the house collapsed. There was no electricity in our community, nor did we have safe ablutions. We had no access to clean water and used to collect water from the stream.

In 2011, the Department of Human Settlements (DHS) built us a house. All children were assisted by the War Room to obtain Identity Documents and birth certificates. The Department of Water Affairs and Forestry (DWAF) helped establish a food garden tunnel and planted fruit trees. We received an environmentally friendly stove from the Greengel Company. We make use of pre-paid electricity and now have upgraded ablution facilities thanks to the installation of two water tanks.

By 2014, we are now out of poverty. Our change agent is now economically active having qualified as a professional nurse, thanks to the eThekwini Metro learnership programme. We continue to receive child support grants and the old age pension grant. All children attend no-fee paying schools and receive nutritional support at school. The tunnel garden provides us with food security together with our earned income. We are glad to report that we are out of poverty. We are forever grateful to the War Room.

Besides this household in Msinga, since 2008, through ongoing efforts of the War on Poverty initiatives, 6 609 households (28 613 individuals) were profiled in the poorest wards in the Msinga Local Municipality (OTP, 2015). Households in these wards are slowly overcoming entrenched poverty through access to government services, such as birth certificates, Identity Documents, social grants, housing, health care, among others, and improving their livelihoods, and moving out of poverty.

The OSS model has been lauded as a best practice model by the South African Deputy President, Mr Cyril Ramaphosa, PEPFAR, UNAIDS, and other provinces that have launched this model. The Deputy President’s office has based its “Best Practice Guidelines for the Implementation of an Integrated Service Delivery Model” on the OSS model.

The OTP’s five-year review is based on narratives from beneficiaries and stakeholders and on data from government departments. While the review provides anecdotal data, there is a dearth of research on OSS and service delivery models in the South African public service. Ndlovu’s (2013) study raises the need for further research using a larger sample with employees across the service delivery value chain, including the municipal ward level. Additionally, research on OSS needs to include social partners and communities as OSS is about collaboration between government and communities.

### 5.2 Inter-governmental collaboration

The success of the OSS model is contingent to the involvement of a range of government and civil society stakeholders. Municipalities are key stakeholders, however, delays in municipal service delivery negatively impact the functionality of OSS. The understanding of Mayors of the OSS model is uneven: while some Mayors support OSS, others do not. Furthermore, provincial departments’ irregular or non-attendance at War Room and task team meetings leads to poor resolution of the service delivery issues identified by the War Rooms. Also, at times there is a lack of response from the responsible departmental manager once issues are referred to them or the departments’ planned interventions are delayed. While the OSS receives good support from several civil society social partners, their funding has eroded over time.

While most (93%) senior provincial manager respondents (n=54) were aware and participated in the OSS, fewer (59%) district level counterparts (n=22) showed the same level of awareness and participation (Ndlovu, 2013). These district managers have a vital task in implementing government programmes at the local level. These results typify the challenge in government that “decisions made at strategic level do not seem to trickle down to the operational level where the implementation of those decisions should take place (Ndlovu, 2013).”

Further, the study indicates that the majority of senior manager respondents indicated that OSS has not increased decentralization of decision-making. The study recommends that the OTP and Provincial Treasury should introduce a strategic planning and budget planning process to integrate the OSS with the provincial-wide processes. Departments at district and provincial levels are either not optimally using the information or not at all in their planning, monitoring and evaluation of their respective sector outcomes.

While OSS promotes bottom-up planning and data collection, several provincial departments continue with the mainstream top-down governance processes – illustrating the dynamic tension between the OSS change initiative and the ongoing business-as-usual mindset of government departments.

### 5.3 Resourcing the OSS

Resource and budget allocations at a human and material level raise serious questions on the sustainability of Operation Sukuma Sakhe.

The success of the OSS model is integrally linked to the effectiveness of fieldworkers. Until their needs (including recognition and appreciation) receive attention, the objective of people-centric and integrated service delivery will falter.

A number of issues influence the effectiveness of the fieldworkers in OSS: Firstly, there are too few fieldworkers in most War Rooms. The spread of fieldworkers is thin as wards could cover vast areas with many households. Secondly, there are a number of human resource administrative issues relating to fieldworkers, as they are not government employees their conditions of employment is unstable. Thirdly, the issue of rank and professional status (highly valued in government as it bestows power and privilege) irks the CCGs as it leads to poor communications and frayed relationships with public health clinic nurses. A CCG shares her frustration: “The clinic nurses look down on us as unqualified. They don’t respond to us. The clinic refuses to share HIV/AIDS statistics with CCGs.” Fourthly, as the “foot soldiers”, CCGs are the first interface with households, building rapport and caring relationships with households; however, at times they experience resistance from some household members who refuse to provide information for the household profile or decline receiving support or show resistance to changing behaviours.

Physical structures, infrastructure and equipment are limitations in establishing War Rooms. Existing resources employed by the provincial government, such as used furniture was sent to War Rooms. For the first three years of Sukuma Sakhe, no dedicated budgets were allocated. Only in the 2015/16 financial year, a small budget allocation (R14 million; or 1 million USD) was made to purchase furniture, equipment and computers. In the 2016/17 financial year, R4 million (or 290 000 USD) was allocated. The resource insufficiency has major negative effects on the functionality at many War Rooms.

The OTP OSS has two full-time middle managers. Eight interns capture household profile data. The senior managers in the team have responsibilities beyond the OSS. Local municipalities are not dedicating resources for full-time coordination of the OSS.

Of significance to the issue of resources for the OSS, Ndlovu’s (2013) study shows that almost 90% of the provincial heads of departments and most senior managers (85.5%) at district and provincial departments affirm that budget is important. However, the majority of senior managers and half of the HoDs disagree that departmental budgets have been aligned to OSS priorities.

In the face of some of the challenges outlined above, in particular the structural and systemic contradictions of the dominant hierarchical and bureaucratic governance model, there are key lessons on leadership and rethinking public service institutional design from the OSS change initiative in promoting a people-centered, integrated, collaborative and co-ordinated approach to service delivery.

### 5.4 Leadership is central

A key factor in Operation Sukuma Sakhe’s success is the presence of political champions who have bought into the philosophy of people-centric and integrated service delivery. An early and crucial achievement in 2009 was gaining the buy-in of the provincial government’s Members of the Executive Committee (MECs) as political champions of the programme, and winning over Councilors and Mayors over time. The political champion roles are institutionalized and are an official part of the structure of OSS.

Through the strong leadership of former and current Premiers, OSS promoted accountability across the provincial government, together with a central message of integrated service delivery—a challenge to the entrenched silos. Since 2011, the philosophy of Sukuma Sakhe was reinforced, identifying weaknesses in the system, and making improvements, i.e. institutionalizing the programme. The continuity and stability of political champions, building on their predecessor’s programmes, has strengthened the structures and systems of OSS.

As the KZN OTP’s Dr Fikile Ndlovu points out: “When leadership is strong, we perform well. Leadership is central in OSS. How Councilors see development is important. Where there is no political leadership, officials and community members give leadership. OSS harnesses community leadership, leaders who are actively engaged in community structures.” A key display of political leadership was to take OSS to the people through monthly provincial Cabinet Day visits to a designated district and local municipality. Departmental heads and senior managers accompany the politicians for these visits. During these community visits citizens engage with politicians and senior managers on a range of issues.

However, Ndlovu’s (2013) study highlights that only half of the senior manager respondents at provincial and district levels consider that there is support from senior management in implementing OSS, while a third of the managers’ responses were neutral and a fifth disagreed. The study concludes that without senior managers’ leadership role, “government institutions are likely to continue working in silos, regardless of the enabling frameworks that have been put in place. Operation Sukuma Sakhe is identified as a programme that seeks to integrate service delivery, therefore leadership is important…Operation Sukuma Sakhe will not be as effective unless the issue of leadership is addressed.”

### 5.5 Rethinking public service institutional design

According to the Presidency’s ISDM (2015), in order to achieve integrated service delivery, all departments and stakeholders would need to change the way they currently do things, combine resources and utilize an integrated service delivery approach to plan and implement services. OSS has attempted to achieve integrated service delivery through introducing a matrix structure into government; however, OSS has experienced many challenges due to the ingrained silos and the top-down management mindset, i.e. the public service institutional design and management behaviours and organisational culture.

On whether the provincial departmental organizational structure supports the implementation of OSS, Ndlovu’s (2013) study found that the majority of senior managers (65%) were either neutral (29%) or disagreed (36%), while 55% of the provincial heads of departments’ were either neutral or disagreed. Furthermore, Ndlovu’s (2013) study indicates that half of senior management respondents and 44% of heads of departments identified that culture in government hinders the implementation of Operation Sukuma Sakhe.

Cross-functional teams (comprising provincial government departments, local government, social partners and service providers) are a practical example of integration through the War Room. These teams are able to escalate matters faster than the vertical hierarchies. When fieldworkers or Councilors pick up issues or when community members report issues to the War Room, the fieldworkers then refer the matter to the relevant government department or authority. In urgent cases, the matter is given priority attention by the relevant department or facility.

However, cross-functional teams operate at the fringes of the dominant rigid and hierarchical departmental edifices. Promoting cross-functional teams require governments to rethink how it plans, budgets, allocate resources, assesses performance (currently biased to individuals and not teams) and monitors government initiatives. Greater resourcing is required for integration, coordination and collaboration across government. A mindset shift among politicians and managers is essential. Working in this manner requires government officials to have the requisite technical skills and relational competencies. Collaboration is about relationships. For OSS it is about the relationship between the Ward Councilor, fieldworkers, the War Room convener, social partners, local municipalities and government departments.

Ndlovu (2013) found that all the KZN provincial heads of departments and most senior managers (92.1%) at provincial and district levels agreed that task teams were important in OSS. The study concludes that task teams are “structures not normally found in government but the findings imply that they are an important element of Operation Sukuma Sakhe.” Governments need to recognize and reward officials working in cross-functional teams and the outcomes of these teams.

The current Performance Management and Development System (PMDS) is not designed to appraise teamwork, and as such rewards individual and silo delivery, not integrated service delivery. One way to recognise and reward collaboration of public servants and integrated service delivery is the KZN Premier’s Service Excellence Award, which confers recognition of the best War Room in the province, dependent on its level of functionality.

OSS is working towards creating greater equality among the rank levels when working as a team as the strong rank consciousness and positional power in government is regarded as a major constraint, stifling collaboration. Mindful of the issue of rank, rank or title does not determine the War Room convener and the chairperson of War Room meetings.

The majority of provincial and district senior managers and all provincial HoD study respondents agreed that the introduction of OSS has led to an increase in collaboration (Ndlovu, 2013). The findings indicate that collaboration in delivering services is one area that has improved with the advent of OSS. Furthermore, the War Rooms promote accountability as it forces politicians and officials to account to each other and to the community regarding service delivery.

## 6 Concluding remarks

The South African public service architecture and governance systems are rigid, hierarchical and overly bureaucratic. This industrial age organizational proclivity continues to dominate government institutions in all spheres, embedding centralized and rank-conscious command and control management and leadership styles. Such archaic and ineffectual public service governance structures and management behaviors only serve to perpetuate the stark poverty and inequality, especially in provinces with former homelands, such as KwaZulu-Natal, with huge historical backlog in socio- economic development.

Against this backdrop, over the past five years, the KZN provincial government has attempted to counter the dominant public governance models and approaches to service delivery to the severely marginalised communities and households in the province. Instead, an integrated, bottoms-up, household-centric, and social partnership driven service delivery model – Operation Sukuma Sakhe – was introduced, which built on the achievements of previous programmes addressing poverty. The KZN’s Office of the Premier continued with the War on Poverty programme, despite the withdrawal of leadership support from the programme’s progenitor, the Presidency.

Even though the OSS model challenges the dominant public service governance and management models, it remains trapped within the powerful 20th century dominant narrative of public organizations. It is in the shadow of this narrative that the democratic South African public service has emerged. Despite the structural and systemic contradictions and tensions experienced by Operation Sukuma Sakhe, there are key lessons to draw from this noble change initiative in promoting an integrated, collaborative and coordinated approach to service delivery that supports the South African government’s Batho Pele (People First) values of caring, serving and belonging. Lessons for example, on the importance of both political and public administrative leadership; sufficient human and material resources, in particular community workers on the ground; and rethinking the archaic top-down public service institutional design and planning processes.

The challenge for the public service globally is to deconstruct the rigid bureaucratic and hierarchical governance structures, and to evolve integrated, dynamic and agile structures and systems that are people-centric rather than bureaucrat-centric. OSS bears several lessons for such a shift. As living expression of Chapter 3 of the South African Constitution, relating to co-operative governance and inter-governmental relations, OSS provides a verdant landscape for learning. This initiative needs a platform in public service change discourse and literature.

##### References

- Children’s Institute & Ilifa Labantwana. (2016). South African Early Childhood Review. Cape Town

- Haricharan, S. (2015). Impact of emotional intelligence competencies on leadership performance in the South African public service. Ph.D dissertation. University of Stellenbosch

- Kellis, D.S. and Ran, B. (2013). Modern leadership principles for public administration: Time to move forward. Journal of Public Affairs, 139(1): 130-141

- KZN Ward 4 Benchmark presentation, 2016

- KZN Ward 4 Ward Profile, 2016

- Office of the Deputy President, (2015). Best Practice Guidelines for the Implementation of an Integrated Service Delivery Model

- Ndlovu, N. (2013). Organizational change factors that impact on implementation of Sukuma Sakhe in KwaZulu-Natal. Masters thesis. Management College of Southern Africa

- Province of KwaZulu-Natal. (2012). Operation Sukuma Sakhe: Implementation Model, Guidelines for Coordination. Pietermaritzburg: Office of the Premier

- Province of KwaZulu-Natal. (2015). Operation Sukuma Sakhe: Five-year review. Pietermaritzburg: Office of the Premier

- Noble, M., Zembe, W., Wright, G and Avenell, D. (2013). Multiple Deprivation and Income Poverty at Small Area Level in South Africa in 2011. Cape Town: South African Social Policy Research Institute

- Republic of South Africa. White Paper on the Transformation of the Public Service, Notice 1227 of 1995. Pretoria: Government Printers

- Republic of South Africa. White Paper on Transforming Service Delivery, Notice 1459 of 1997. Pretoria: Government Printers. Robledo, M.A. 2009. Integrating management theory: Using the AQAL model for multiparadigm management research. Journal of Integral Theory and Practice, 4(1): 57-70

- Statistics South Africa. (2012). Census 2011 Metadata, Pretoria: Statistics South Africa

## Acknowledgements

The author acknowledges the following organisations and persons:

- The Programme to Support Pro-poor Policy Development (PSPPD) located at the national Department of Planning, Monitoring and Evaluation for funding the case study on Operation Sukuma Sakhe.

- The Government Technical Advisory Centre (GTAC), an agency of the South African National Treasury, at which the author is a senior advisor.

- The Office of the Premier, KwaZulu-Natal Provincial Government, in particular, Dr Fikile Ndlovu, Chief Director: Priority Programmes and Ms Senzeni Mkhize, Director: Inkululeko Development Project and Operation Sukuma Sakhe for their support with the case study and their valuable input to this paper.

- Councilor Sithembiso Nkuna and his team at the Ward 4 War Room in Lidgetton, in the Umngeni Local Municipality for sharing their stories.