# Study on the Construction of Three-dimensional Risk Identification Model of Public Service Outsourcing in China

1. ZHANG Zhen  2. ZHU Xiao-ning

School of Political Science and Public Administration, University of Electronic Science and Technology of China, Chengdu, P.R. China, 611731

Abstract  Public service is a civil conduct, using the government agency as the employer and contracting the transactional and technical public services to the market or society players. In essence, it is a conduct of introducing competition mechanism into the public sphere. The risk of public service outsourcing will not only cause some economic losses, but also to a greater extent will harm the public interest, reducing the credibility of the government. Risk identification model is built to better identify the risks, as well as their types, sizes and nature. The aim of this study is to achieve comprehensive risk identification through the construction of the risk identification management model of public service outsourcing, thereby contributing to a systematic risk assessment, dynamic risk monitoring and scientific risk management. This study focuses on the design of the three-dimensional risk identification model of public service outsourcing. The model involves three dimensions, which are of how to divide the risk axes, how to locate the risk points and how to integrate the risk elements. Then, through the three angles of demonstrations to the three dimensions of the model, the science of the model can be proved and finally the conclusions of this study has been conducted.

Key words  Public service, Outsourcing, Risk identification, Model

## 1 Introduction

Public service is a civil conduct, using the government agency as the employer and contracting the transactional and technical public services to the market or society players. In essence, it is a conduct of introducing competition mechanism into the public sphere[1]. The core can be summarized as the following aspects. Firstly, public service outsourcing is a sublation of the traditional government monopoly supplying model of public services, which requires introducing market or non-profit organizations as third-party body in the supply of public service, in order to achieve the diversification of supply. Secondly, the nature of public service outsourcing is the introduction of competition in the market; by introducing competition to break monopoly, each subject is in a fair competition environment in public service provision. Thirdly, there are several manifestations of public service outsourcing; and contract outsourcing is a form which is very important, but in essence not the only form. Fourthly, public service outsourcing is not beyond government responsibility, but the government responsibility to achieve the transformation in the realization. Government still bears the roles of decision-makers, supervisors and many others’, as well as prevents and overcomes the various problems that may arise in outsourcing processes, so as to promote continuous improvements in the quality of public services delivery.

Distinguished from other types of outsourcings, the particularity of public service outsourcing is that its risk will not only cause some economic losses, but also to a greater extent will harm the public interest, reducing the credibility of the government. However, there are few specialized researches on public service outsourcing risk currently. The researches are usually scattered in all kinds of materials from different perspectives as the problems lying in public service outsourcing. There are researches from the principal-agent relationship perspective, the definition of risk perspective or the process of outsourcing perspective. Overall, domestic demand for the risk of public service outsourcing is still in preliminary stage, with less related research, lacking of deep research. And most of the researches are on the whole risk management process of public service outsourcing, and have not been refined to the specialized aspects, such as risk identification, risk analysis, risk assessment and risk response. Moreover, because of different research points of view, theoretical bases and subject areas, it is difficult to clearly identify the various types of public service outsourcing risks in all the stages of outsourcing, as well as their types, sizes and nature. Therefore, before conducting in-depth research on the public service outsourcing risk management, it is believed that accurate and effective risk identification is the basic premise, which can be served as the original intention of this research.

Risk identification model is built to better identify the risks, as well as their types, sizes and nature. And its purpose is to better respond to and manage risk. However, the current academic researches on risk identification mainly focused on risk identification methods, risk identification techniques, risk identification measures and so on. And the researches on risk identification model mainly focused on the domain of business management, such as financial or project service outsourcing, and not related to the domain of public administration. From the current research achievements of risk identification model, what the researches focus on is the construction of all kinds of mathematical models as well as risk quantification. Basically there is no research on the construction of risk identification model from the management perspective. However, for the risks of public service outsourcing, many of them are difficult to be quantified. And for the risks in public sectors, the applicability of the above models is so weak that it is necessary to build a management model exclusively aiming at the risk identification of public service outsourcing.

Firstly, from the theoretical point of view, this research can enrich the existing public service outsourcing researches, and clarify the researches on public service outsourcing risk under several research perspectives, disciplines and theoretical bases. And the researches on the issue of public service outsourcing risks have been refined to the risk identification. Secondly, this study can solve how to identify various types, stages, and levels of public service outsourcing risks comprehensively, accurately and systematically in theory, and how to integrate the risk factors effectively, which can lay foundation for the subsequent risk analysis, risk assessment and risk response. In addition, from the practical point of view, the construction of the model of public service outsourcing comes from these problems such as different standards of risk identification, pertinence of risk prevention measures, static nature of public service outsourcing risk identification, scattered public service outsourcing risk identification results. This study will be of some assistance to solve the above mentioned problems. Therefore, this study is intended to clarify what the public service outsourcing risks in practice are caused by and to whom, which is able to provide references for government decision making in practice so as to take preventive measures to better respond to risk in the entire outsourcing process.

## 2 Theoretical framework and methodology

### 2.1 Theoretical basis

This study not only refers to the public choice theory and the new public management theory in the field of public service outsourcing, but also the risk society theory and the risk management theory in the field of risk identification.

The public choice theory believes that public services can be provided by the government or the society. Therefore, when public services are provided, breaking the boundaries of public and private sectors and destroying the government monopoly are helpful to form the free competition between the government and society and between the public and private. At the same time, they can give the public the right to choose. However, according to the new public management theory, private sector management ideas and management methods are applied in the government management activities, which is aimed at establishing the enterprise-oriented government[2]. In dealing with the relationship between the government and the market as well as the relationship between the market and the society, being different from the traditional administration, the new public management theory can offer a set of new ideas. It believes that in addition to the bureaucracy, other departments also have these functions in the provision of public goods and services. Service delivery ultimately depends on a route in the most economical way to achieve the public demand for public goods.

The concept of risk society proposed firstly by the German sociologist Beck is used to understand the modern society. In his opinion, there are two salient features of the risk society. The first one is the anthropogenic uncertainty of continuous spread. The second one is the complex, contingency and divisive of social structures, institutions and relationships[3]. Consequently, the risks that modern society have are completely different from those in the ancient society, because they are the product of modernization. Risks of the risk society include economic, political, ecological and technological risks. Obviously distinct from previously natural risks, they are mostly artificial risks. Risk management is a management process that is about how to minimize the risks and hazards in a risky environment[4]. The objective of risk management is to obtain the maximum security assurance in the minimum cost. Therefore, it is not only a safety production issue, but also a set of solutions including risk identification, risk analysis, risk assessment and risk response, which involves finance, safety, production, equipment, logistics, technology and other aspects of systems engineering. Risk identification studied in this paper belongs to the first basic link of the risk management process.

### 2.2 Methodology

The model is a form of expression abstracting system, processes, things or concepts, and modeling is a process that uses the model to describe causality or mutual relations between them. This paper takes advantage of the method of modeling to abstract the object of study and make relationship logical, which leads to a more clear and concise study of how to effectively identify the risks of  public service outsourcing, as well as their types, sizes and nature.

## 3 Research hypothesis

It can be seen from the research review on public service outsourcing and risk identification models in the previous part that it is necessary to construct a set of specialized risk identification management model for public service outsourcing. Thus, the basic assumption has been put forward: Constructing a three-dimensional risk identification model of public service outsourcing, which can identify the risks, as well as their types, sizes and nature effectively.

The model is divided into three dimensions on the whole, the division of risk axes, the location of risk points and the integration of risk elements. And the model is shown in Figure 1. In the model, the risk axes can be divided into category axis, time axis and level axis based on the category and process of public service outsourcing as well as outsourcing risk level. The risk point is located in the space composed of these three axes. Seen from the model structure, when a risk point is located, what kind of public service outsourcing will lead to what extent risk and when it will happen can be known. After locating the risk point, it also needs to integrate all kinds of risk elements, including risk sources, risk types, risk characterizations, risk events, risk losses, risk causes and risk levels. Static integration of risk elements can be achieved through the establishment of risk list, and dynamic integration of risk elements can be achieved through the risk point trajectory in the space composed of three axes. In addition, the changes in risk can be identified according to the changes in point emotion, and the risk prone areas can be identified according to the aggregation of points.

Firstly, the category axis is designed according to the category of public service outsourcing, and it can be divided into business outsourcing, licensing outsourcing, customized outsourcing and public outsourcing. The time axis is designed according to the process of public service outsourcing, and it can be divided into three stages, decision-making, implementation and evaluation. The level axis is designed according to risk matrix, and it can be divided into four levels, low, medium, high and severe.

When the kind of outsourcing that leads to risks and its occurrence time is known, the mapping point M of this risk point on the plane XOZ, which is composed by category axis and the time axis, can be fixed. Then, according to the likelihood and impact of the risk, the point N can be fixed on the level axis. Thus, the risk point P can be fixed in the space. The mapping points of the point P on the plane XOZ and YOZ are respectively P “and P” .

When the risk point P is fixed in the model, the risk elements which it contains, such as risk source, risk type, risk characterization, risk event, risk loss, risk cause and risk level, can be found in risk list, so as to grasp the risk information fully and effectively and to achieve the static integration of risk elements. Meanwhile, for a specific public service outsourcing project, the number and position of the risk point changes with time. Therefore, by observing the trajectory of a risk point, or the occurrence time of different risk points, or the distribution of risk points of the entire project, a lot of information about changes in risk point motion can be obtained, so as to achieve dynamic integration of risk elements.

Figure 1  Construction of three-dimensional risk identification model of public service outsourcing

## 4 Scientific demonstration of three-dimensional risk identification model of public service outsourcing

Scientific demonstration of the model can be achieved by demonstrating three dimensions of the model respectively.

### 4.1 Rational demonstration of the division of risk axes

The rationality evaluation criteria of the division of risk axes ought to include the following aspects. Firstly, whether the division of risk axes can distinguish the particularity of public service outsourcing from other outsourcings. Secondly, whether the division of risk axes can identify various risks in the process of public service outsourcing dynamically. Thirdly, whether the division of risk axes can identify the source and size of risks. The following part will successively demonstrate the rationality of the three risk axes.

4.1.1 Rational demonstration of the category axis

The division of the category axis is borrowed from the division of contract outsourcing by scholar Chen Qixing in The Thinking to Enhance the Grass－root Government Outsourcing Practice: Based on Shanghai City. In this article, he believes that different types of contract outsourcings of local government can be divided according to two dimensions. The first is the nature of outsourcing service, whether for the government or for the public. The former can be called indirect public service, and the latter can be called direct public service. The second is the subject to undertake the outsourcing, whether the enterprise or the non-governmental/non-profit organization (NGO/NPO). The former has certain nature of profit, while the latter is mainly public and non-governmental[4]. According to the two criteria, government contract outsourcing can be divided into four types. The first one is business outsourcing, which the service facing to the government and is mainly undertaken by the enterprises. The second one is licensing outsourcing, which the service facing to the public and is mainly undertaken by the enterprises. The third one is customized outsourcing, which the service is provided by the government and is undertaken by the NGO/NPO. The fourth one is public outsourcing, which the service is facing to the public and is undertaken by the NGO/NPO. The classification by Chen Qixing is designed for contract outsourcing, which is the most important form of public service outsourcing. But according to the definition of public service outsourcing, it can be found that, in fact, the classification can be applied to all the public service outsourcing. Because all kinds of outsourcings can be included into the two dimensions: Object-oriented is government internal or external, while the bearing subject of service is the market or the social players. What differs from other service outsourcings is that its object-oriented and not only one type of bearing subject. General outsourcings mainly come from domestic demands, and will choose the enterprise to undertake service out of economic benefits. Therefore, the classification of public service outsourcing also reflects the public nature distinguished from other outsourcings. The category of public service outsourcing in this paper is shown in Table 1.

Table 1  Category of public service outsourcing

| Bearing subject Object-oriented | Market player | Social organization (NPO/NGO) |
| --- | --- | --- |
| Government internal | Business outsourcing | Customized outsourcing |
| Government external | Licensing outsourcing | Public outsourcing |

4.1.2 Rational demonstration of the time axis

The division of the time axis conforms to the operational process of public service outsourcing. Privatization Master Savas has summarized the practical experiences of many countries, and grouped public service outsourcing into the 12 following steps. (1) Consider implementing the outsourcing contract; (2) select the services to be outsourced; (3) conduct a feasibility study; (4) promote competition; (5) understand the bidding intentions and qualifications; (6) make a plan of employees; (7) prepare for the details of bidding contract; (8) conduct public relations activities; (9) plan for competition with managers involved in; (10) conduct fair bidding; (11) evaluate the tender and sign the contract; (12) monitor, assess and promote the performance of contract[5].

Smith has made a program list for the implementation of public service outsourcing. (1) Evaluate the funding for certain public service; (2) determine the legitimate beneficiary of the service; (3) determine the legitimate provider of the service; (4) select market environment; (5) determine the performance appraisal criteria; (6) link the rewards to the costs; (7) determine other aspects of the contract; (8) set management structure[6].

According to the above procedures of public service outsourcing, public service outsourcing is divided into three stages in this paper, decision-making, implementation and evaluation. The main task in decision-making stage is to make outsourcing decisions, choose the services to be outsourced, conduct feasibility study, and prepare for the details of bidding contract. The main task in implementation stage is to determine the outsourcing contractor, sign the contract, and the contractor fulfills the contract requirements. The main task in evaluation stage is the contractor provides outsourcing results to the contracting, the contracting checks the results and gives feedbacks, and finally settles the fund.

The time axis is designed based on the three stages, so as to clearly predict every risk in each period and prepare for the risk response in advance.

4.1.3 Rational demonstration of the level axis

The design of the level axis is to quantify the risk through risk assessment results, and reflect the nature of risk through risk response measures. In this study, risk matrix is adopted to divide the risk levels. Risk matrix is an effective risk management tool, using qualitative and quantitative analysis to consider the two risk factors, which are likelihood and risk impact, in order to assess the level of risks[7], as is shown in Figure 2.

Firstly, list all the potential risks of a project. Then, hire an experienced panel of experts on risk assessment, and estimate the likelihood of these potential risks successively, using low, medium, high or figures 0-10 or percentage as the standard. With the same method, the panel estimates the impact of these potential risks. Finally, calculate the risk level based on its likelihood and impact.

Based on the risk matrix, the risk level of public service outsourcing can be classified as four levels, low, medium, high and severe. At the same time, the nature of risk has also been confirmed. Among them, the low-level risk belongs to reactive risk, with no need for prior prevention.

While the middle-level, high-level and severe-level risks belong to preventive risk, with great need for good prevention before the occurrence of risk[8]. The risk response measures that various levels of risk should be taken are shown in Table 2.

Table 2  Risk levels of public service outsourcing based on risk matrix

| Risk nature | Risk level | Risk response |
| --- | --- | --- |
| Preventive risk | Severe | At the cost of preventing its occurrence, if the cost is greater than the acceptable range, then abandon outsourcing. |
|  | High | Arrange for a reasonable fee to prevent its occurrence. |
|  | Middle | Take reasonable measures to prevent its occurrence or minimize its impact. |
| Reactive risk | Low | Take measures when the risk occurred, or even no need to take action. |

### 4.2 Reliable demonstration of the location of risk points

The reliability evaluation criteria of the location of risk points ought to include the following aspects. Firstly, whether the location of risk points is based on comprehensive and accurate risk information collection. Secondly, whether the location of each risk point is unique. Thirdly, whether the location of each risk point is accurate. The following part will successively demonstrate the reliability of the location of risk points.

First of all, based on the collected risk information, the coordinate of the risk point on the category and time axis can be fixed. In the process of collecting risk information, subjective source information collection methods will be applied, such as brainstorming, Delphi method, expert interviews, as well as some objective source information collection methods, such as SWOT analysis, project inspection method and assuming analysis. Combined subjective with objective source information collection methods together, we can ensure that the collected information is comprehensive and accurate, which can guarantee the accuracy of positioning points. Then, based on the risk matrix, the coordinate of the risk point on the level axis can be fixed. When a point on a plane and another point perpendicular to the plane are fixed, the location of the risk point in space can be fixed with unique position. With this method, the location of all the risk points is unique and accurate.

### 4.3 Effective demonstration of the integration of risk elements

The effectiveness evaluation criteria of the integration of risk elements ought to include the following aspects. Firstly, whether the integration of risk elements is comprehensive. Secondly, whether the integration of risk elements is systematic. The following part will successively demonstrate the effectiveness of the integration of risk elements. First of all, the list of risks includes the information of risk source, type, characterization, event, losses, cause and level, which encompasses the various risk elements. Meanwhile, each risk point fixed by the model is able to find the corresponding entry in the risk list. Therefore, we can compile a risk list of a project so as to better manage and respond to risks.

Then, with the help of three-dimensional positioning technology in computer field, the trajectory of points can stimulate the position and motion of each risk point, as well as the final distribution. And with the help of risk list, we can identify the various elements of risk points as well as all the risks of the project accurately, and outline the content of each risk, so as to provide adequate support for risk response and management of public service outsourcing.

## 5 Conclusions

According to the above analyses and demonstrations, the conclusions of this study have been conducted.

Firstly, the model constructed by the category, time and level axis makes it easy to position the risk point in space, as well as identify the risks, as well as their types, sizes and nature.

Secondly, as the support of the model, risk list can effectively integrate all the risk elements contained in the risk points, which are clarified from the public service outsourcing projects, so as to provide the basis for risk response.

Thirdly, with the help of three-dimensional positioning in the field of computer technology, it is efficient to stimulate the position and motion trajectory of every risk point, as well as their final distribution, which is beneficial to the whole process of risk monitoring and management.

Fourthly, this paper has constructed a logical management model for risk identification, if the contents represented by the three axes are replaced, the three-dimensional risk identification model might be extended to other fields.

##### References

[1]	Zhao Quan-jun. Study on the Government Role in Public Services Outsourcing [J]. Study and Explore, 2011(4): 80 (in Chinese)

[2]	Ulrich Beck. Risk Society [M]. Yilin Press, 2004 (in Chinese)

[3]	Yi Na, Tan Zheng-bi, Xiong Dao-jun, et al. Study on Medicine Risk Management from the “Houttuynia Event” [J]. Herald of Medicine, 2008(9):1136 (in Chinese)

[4]	Chen Qi-xing. The Thinking to Enhance the Grass-root Government Outsourcing Practice: Based on Shanghai City [J]. Chinese Public Administration, 2012(11): 77-78 (in Chinese)

[5]	Tan Shui-ping. Study on Citizen Participation in Public Service Outsourcing [D]. Changsha: Hu Nan University, 2012 (in Chinese)

[6]	Yin Ya-qiong. Study on Risk Prevention of Public Service Outsourcing [D]. Yunnan University of Finance, 2011 (in Chinese)

[7]	Chang Hong, Gao Yunli. Risk Matrix Method in Project Risk Management [J]. Industrial Technology & Economy, 2007(11): 134 (in Chinese)

[8]	Heman B. Dutch Leonar, AmoId M. Howit, Zheng Huan. Integrated Risk Management: Preventive Disaster Recovery [J]. Journal of China National School of Administration. 2011(4): 124-127 (in Chinese)