# Research on Project Management Mode of 
Post-Wenchuan Earthquake Restoration and 
Reconstruction of Housing for Urban Residents

1. ZENG Yu-cheng  2. GOU Yong-jie  3. XIE Yi  4. WU Ke

1. 3. 4 The Business School, Sichuan University, Chengdu, P.R. China, 610064  
2. The People’s Government of Yanting County, Sichuan Province, 621600

Abstract  The authors of this thesis are engaging in the planning, project management, and theory and methodology study of post-Wenchuan earthquake reconstruction. Considering the practical problems in the project management mode of post-quake reconstruction of housing for urban residents, elaborating the concept and characteristics of it, this thesis further analyzes the existing problems during the implementation of different post-quake urban housing reconstruction project management modes, which include maintenance and reinforcement, in-situ reconstruction, ex-situ reconstruction, reconstruction and development, and policy-based housing reconstruction, and optimally redesigns the above project management modes. This thesis also proposes supporting mechanisms for the effective enforcement of project management mode of post-quake restoration and reconstruction of housing for urban residents. All above will provide positive factors to the implementation of post-quake urban housing reconstruction project management mode, fasten the pace of urban housing reconstruction, and offer scientific and constructive suggestions to post-quake reconstruction with valuable reference.

Key words  Wenchuan devastating earthquake, Housing for urban residents, Restoration and reconstruction, Project management, Optimal design on mode

## 1 Introduction to project management of post-quake restoration and reconstruction of housing for urban residents

The Wenchuan devastating earthquake has caused 896.43 billion Yuan in direct economic losses nationwide. Cities, towns, and urban and rural settlements in Sichuan Province were heavily damaged. Towns and counties like Beichuan and Yingxiu were razed to the ground. Totally 978,000 urban households in Sichuan Province were affected by the earthquake, among which 19.33 million square meters urban houses collapsed and 68.767 million square meters were heavily damaged. According to the post-quake planning, Sichuan will “build 3,500,000 new units and restore 1,000,000 units of housing for urban residents, and recover township and county medical institutions. The total investment reaches 1200 billion RMB”.[4] It can be seen that post-Wenchuan earthquake restoration and reconstruction of housing for urban residents (hereinafter referred to as “post-quake urban housing reconstruction”) is a long-term and arduous work.

### 1.1 The status quo of the post-quake restoration and reconstruction project management

The author chaired the planning on post-quake restoration and reconstruction, and has been engaging in post-quake restoration and reconstruction project management and its theory and methodology study. The research results of the author’s early “Research on Project Management Mode of Post-Wenchuan Earthquake Restoration and Reconstruction of Rural Housing” have been applied to the work on rural housing restoration and reconstruction and obtained positive effects. Nevertheless, we have found from practical work and extensive survey, when choosing the project management mode for post-quake urban housing reconstruction, most quake-affected areas adopts governmental “administrative project management mode”. This mode played particularly active role during the early stage of earthquake relief, but hardly is it effective in the restoration and reconstruction of urban housing. Its limitations list as the follows.

(1) The administrative project management mode can hardly adapt to the complex natural situations, destroyed infrastructures, and bad management environment, which the project management of post-quake urban housing reconstruction are facing.

(2) The sources of funding for post-quake urban housing reconstruction vary a lot, including the central financial subsidies, local governments’ allocation, supporting partner regions’ investment, and quake-affected people’s self-raising fund etc.

(3) A large number of people with different backgrounds are participating in the post-quake urban housing reconstruction project. There are governmental officials, professional experts, supporting partner institutions and so on. It is difficult to use the administrative project management mode to deal with the complexity like cross investment and management.

(4) Many post-quake urban housing reconstruction projects are currently poorly managed. There is no clear line between the functions of the government and enterprises. This is neither conducive to the fair competition in the market, nor helpful to the change of government’s functions.

(5) Not a few local governments use the mode of “daily management plus contingency management” to deal with the post-quake urban housing reconstruction. It can’t provide good guidelines to the implementation of post-quake urban housing reconstruction.

It can be seen from the above analysis that the existing project management mode for the post-quake reconstruction can hardly adapt to the current needs of the project management of post-quake urban housing reconstruction.

### 1.2 The current study on this issue home and abroad

At present, there are few references about post-quake restoration and reconstruction research, among which Xu Jiuping proposed that post-quake reconstruction, is an extremely complex systematic work whose completion requires multi-coordination and cooperation [1]. Gao Yongxiang and some scholars suggested that to apply “command headquarter” management mode to post-Wenchuan earthquake restoration and reconstruction is deficient in many aspects. Project management mode should be introduced to meet the shortfalls[2]. However, they didn’t make specific project management mode of post-quake reconstruction. Lu Zhenheng summed up post-quake management mode of Japan, and pointed out that Japanese governments at central and local levels establish specialized agencies to fulfill command, instruction, and coordination responsibilities in post –quake reconstruction project management[3]. After his study on the post-quake reconstruction management of Pakistan, Xu Fuhai concluded that the government of Pakistan initiated “self-reconstruction strategy” that encouraged people to build their home by themselves, and meanwhile provided fund, technology and instructions to quake-affected people. They also established post-quake restoration and reconstruction commission who was supervising construction quality[4]. Zhang Tao proposed new method on the fund management of post-quake non-operational projects invested by the government, after his research into post-Wenchuan earthquake reconstruction management[5]. Experts like Liao Yunfen have already realized that non-governmental organizations (NGO) are necessary and more important than before in contingency intervention and post-disaster reconstruction, for their own advantages. However, they are weak in legal protection and organization, as well as participation quality[6]. Xu Zhichu deemed that government, market, and NGOs including individual volunteers are the main force in post-quake reconstruction. To ensure strong, orderly, and effective post-quake reconstruction, we must properly deal with the relations not only between government and market, but also government and NGOs[7]. On the basis of systematic management theories, Zhao Wenchuang and some experts proposed project management index that includes “one starting point, two centers, and five guarantees”. They also built up post-quake reconstruction project management system, to which they offered implementation suggestions[8].

We can draw from above that current scholars and experts haven’t done systematic research on the project management mode of post-quake restoration and reconstruction.

### 1.3 The necessity of the research on project management mode of post-quake restoration and reconstruction of housing for urban residents

It can be seen from the previous analysis that there are many problems existing in the process of post-quake restoration and reconstruction. In addition, the current study on this topic, home or abroad, is still not enough. To learn about the project management mode of post-quake urban housing reconstruction is very necessary whether now or in the long run.

(1) The study can solve the most urgent problem in the project management of post-quake reconstruction. The existing problems have already heavily affected the reconstruction of the housing for urban residents. This has become a pressing issue that we must deal with. In this case, the research on project management mode of post-quake reconstruction will help with the establishment of a suitable urban housing reconstruction management mode. As well it will guarantee the strong, orderly, and effective implementation of reconstruction work, and be conductive to reconstruction problem solving.

(2) The study will provide valuable reference to global disaster prevention and relief. Although we are not able to accurately forecast disasters, we can draw experience and learn lessons from the past losses. We must utilize our wisdoms to analyze the problems emerge during post-quake reconstruction, so as to minimize the earthquake damage and to provide useful reference to similar researches.

(3) The study will fill the gap in post-quake reconstruction project management mode research. There is no scholar or expert, home or abroad, did such research. This thesis is trying to figure out a new project management mode of post-quake reconstruction for the first time.

(4) The study will offer useful reference to the establishment of theoretical system of post-quake restoration and reconstruction project management. This thesis is focusing on the basic operation, technology, and process of project management mode of post-quake urban housing reconstruction. It is not only the theory guideline and practice instruction for the project management of post-quake reconstruction, but also a helpful reference to China’s project management theoretical system.

### 1.4 The concept of project management mode of post-quake restoration and reconstruction of housing for urban residents

1.4.1 The definition and characteristics of post-quake urban reconstruction project management

(1) The definition for post-quake urban housing reconstruction project

The so-called post-quake urban housing reconstruction project refers to the systematic work, which consists of in-situ and ex-situ reconstruction or reinforcement of the urban housing that are damaged in the quake-affected areas. The reinforcement hereby refers to the strengthening and repair of urban housing that was damaged to a certain degree in the earthquake, evaluated by the experts concluding no major problems, and could be used again. The reconstruction means the demolishing of urban housing that were heavily damaged in the earthquake, and must be rebuilt in-situ or ex-situ after the experts’ evaluation confirming major problems.

The management on post-quake urban housing reconstruction project refers to the organization, plan, instruction, and coordination of the planning, design, assessment, and implementation of post-quake urban housing reconstruction project, using all means of know-how, technology, measures and methods, aiming at meeting or satisfying the interests of project stakeholders.

(2) The characteristics of the post-quake urban housing reconstruction project management

① The hardship. In the process of post-quake urban housing reconstruction, it is difficult to balance and coordinate among the owners who are living in the same block and have different troubles and interests demands. This has made the demolishing and rebuilding work rather hard.

② The ethnic complexity. Many areas like Wenchuan and Beichuan in Sichuan Province are regions with ethnic groups. We must take the ethnic characteristics into consideration, act according to local conditions, and give specific guidance to different localities, avoiding simple repetition.

③ The time emergency. Housing for quake-affected people is always on top agenda for post-quake reconstruction. The national government called for the completion of the task within three years. The time emergency is self-evident that to finish such large scale urban housing reconstruction with the shortest time period.

④ The long term work. Large-scale post-quake urban housing reconstruction is a long-term and complex task, which must meet the quake-affected people’s current needs, and take into account the permanent sustainable development of quake-affected people and areas.

1.4.2 The definition and characteristics of project management mode of post-quake urban housing reconstruction

(1) The definition for project management mode of post-quake urban housing reconstruction

The project management mode of post-quake urban housing reconstruction is a comprehensive project management system. It is based on the inherent objective laws and characteristics of post-quake urban housing reconstruction project, and adaptive to such rules and theories. From the perspective of its content, it is the whole management process of post-quake urban housing reconstruction, including the project proposal, the feasibility study, the engineering design, the construction work, and the operation. From the perspective of its characteristic, post-quake urban housing reconstruction is fixed assets investment management.

(2) The characteristics of the project management mode of post-quake urban housing reconstruction

① It reflects the interests of all parties. The project management mode firstly respects and represents the will of quake-affected people, and meets their requirements as much as possible. Secondly, the planning of reconstruction must start from the perspective of urban development strategy. Finally, it takes into account the interests of parties who have participated in post-quake urban housing reconstruction.

② It is collaborative in management. Post-quake urban housing reconstruction involves various aspects and different subjects. It requires comprehensive integration of cross-categories, and asks for exchanges and cooperation among actors, resources sharing, and collaboration.

③ It is a complex system. The devastating earthquake makes the construction technology and management rather complicated, and causes uncertainties and risks in the process of reconstruction project implementation.

### 1.5 The categories of post-quake urban housing reconstruction project

When compared with rural housing reconstruction, post-quake urban housing reconstruction is much different. It is more complicated in categories, which include reinforcement, in-situ reconstruction (self-build, joint cooperative build, and allied build), ex-situ reconstruction, reconstruction and development, and policy-based low-cost housing construction. In practice, for the convenience of post-quake reconstruction project management, we generally divide urban housing reconstruction into two categories. One is reinforcement, and the other is new-construction.

(1) Reinforcement. This category includes the urban housing, evaluated by the experts, which can be reused after reinforcement and repair.

(2) New-construction. This category refers to those urban housing which were heavily damaged in the earthquake and can’t be reinforced, according to the experts’ evaluation results. It consists of in-situ reconstruction (self-build, joint cooperative build, and allied-build), ex-situ reconstruction, reconstruction and development, and policy-based low-cost housing reconstruction.

### 1.6 The purpose of the research on project management mode of post-quake urban housing reconstruction

Post-quake urban housing reconstruction is a complicated systematic engineer, which covers an extensive range and contains many influence factors. The research purpose of this topic is listed below.

(1) To build up a simple project management mode of post-quake urban housing reconstruction. Considering that the post-quake urban housing reconstruction project management requires coordination among different departments and agencies, and is a multi-level, multi-dimensional, and multi-functional system with complexity, we abstract key factors and processes from practical system, describing various factors and their relations according to certain standards and principles, to make the contents and management approaches of the mode can be easily understood by project-related parties. Finally we figure out a project management mode of post-quake urban housing reconstruction, which is clear in responsibility, power and interest, and simply in implementation.

(2) To build up a mode that can simultaneously coordinate the interests of all reconstruction project participants. Post-quake urban housing reconstruction is rather complex, for different people and interest groups have different appeals, which need balance and collaboration. Thus we must find out a project management mode, which is able to coordinate or satisfy the interests of all urban housing reconstruction project participants.

(3) To build up a control mode of post-quake urban housing reconstruction. The quality, progress, and budget are difficult to control in current reconstruction work. To compose the project management mode of post-quake urban housing reconstruction, we must adhere to the logic relations among quality, progress, and budget, to design a “triple control” mode of post-quake urban housing reconstruction project.

(4) To build up a supervising mode of post-quake urban housing reconstruction. Response to the existing problems like the absence of project body, the runaway investment, supervision failure, and the “Build, Manage, Operate” (BMO) three-in-one issue, when building up the project management mode of post-quake urban housing reconstruction, we must establish its supervising mode according to the principle of separating the powers of the investor (owner), the constructor, and the project administrator (surrogate constructor).

## 2 The existing problems of project management of post-quake restoration and reconstruction of housing for urban residents

Due to the lack of the experience in reconstruction of post-quake project management and the knowledge of dealing with the project management according to market economy, governments at all levels still adopt the project management modes like the “administration project management mode” or the “daily management plus contingency management”. There are mainly two types that are summarized below.

### 2.1 The current structure and existing problems of the “project management mode at administrative level”

2.1.1 The current structure of the “project management mode at administrative level”

Currently, the post-quake restoration and reconstruction of housing for urban residents is adopting the “project management mode at administrative level” by the government. This mode is different from the rural housing reconstruction project management mode, which is defined into two sub-patterns. One is for the reinforcement, and the other is for permanent housing reconstruction. For the reconstruction project of urban housing, the reinforcement, in-situ reconstruction, and ex-situ reconstruction are all using the same project management mode. Under such mechanism, the urban housing reconstruction leading group takes charge the overall planning and implementation. A policy group is added up to the organization and responsible for publicity and guidance. Meanwhile, all the sub-groups are targeting on the urban housing reconstruction leading groups at county and township. The organizational layout of this mode is seen below Figure 1.

Figure 1  The current project management mode of post-quake urban housing reconstruction

2.1.2 The existing problems of the current “project management mode at administrative level”

It can be seen from the layout 2.1 that the current post-quake urban housing reconstruction project management mode is completely a governmental “project management mode at administrative level”. There are major problems in this mode.

(1) Too many administrative layers and low efficiency. The preliminary work of the reconstruction, which includes project approval, feasibility study report (FSR), EIA, and construction plan approval, is time-consuming. It usually takes 3-6 months from the reporting of the project to the start of it. Firstly, the township government will examine and audit on residents’ applications, and then the municipal land resources bureau will provide advisory opinions on geologic hazard of the project. Then the township government should apply to the city-planning bureau for land-use red line plan. After the issue of the map and plan, the city-planning bureau will examine and audit the construction scheme. The township government should at last apply for construction planning permit issued by the city-planning bureau, and start construction.

(2) Incomplete quality-control system can’t guarantee the construction quality. Due to the lack of professional design and construction agencies, the quake-affected residents and owners’ committees have to entrust some construction teams with few experience to do the design and constructing work. Adding that there are insufficient quality-supervising organizations, the urban housing reconstruction quality remains in low level.

(3) The lack of cost-control system makes it difficult to control the construction expenses. Hardly helped by professional agencies, the quake-affected residents and owners’ committees can rarely understand the cost structure and its calculation method. They have to in that case sign the contract with the construction party subject to their quoted price. At the same time, there is no specific agency to judge on the rationality of the design and cost calculation, causing the average cost of some cases reaches 800 Yuan per square meters, which is far more than the average level of 715 Yuan per square meters.

### 2.2 The current structure and existing problems of the “project management mode of direct administration”

2.2.1 The current structure of the “project management mode of direct administration”

The direct administration mode is used in the post-quake policy-ensuring urban housing reconstruction. Adopting this mode, municipal or county governments authorized administrative departments as the legal person of the project, who will sign project management contract with the contractor. The project funds come directly from municipal or county finance. The administrative departments as the legal person of the project on one hand have the choosing, managing, supervising, and accepting right on contractors. On the other hand they are also granted the right to allocate the policy-based affordable housing. This mode can be illustrated as the following Figure 2.

Figure 2  The current administrative mode of policy-ensuring 
urban housing reconstruction project

2.2.2 The existing problems of the current “project management mode of direct administration”

It is clear from the above graph that the project management mode of policy-ensuring urban housing is totally a governmental direct administration mode. Below list its problems.

(1) The absence of project main body and the difficulty in implementing responsibilities. The governments greatly lead and involve in most post-quake restoration and reconstruction projects. However, the real beneficiaries and the project owners are mainly quake-affected people. Under such project management mode, it is hard to clarify the main body of the project. This makes the constructors unclear about whom they should be responsible for, and how they could take responsibilities. Thus it’s difficult to implement responsibilities.

(2) The lack of professional project management agency. During the post-quake reconstruction, major duties of the government include not only overall command, planning and coordination, resources allocation, and serving quake-affected people, but also leading the whole process of post-quake urban housing reconstruction. The professional management and service deficiency on reconstruction projects will undoubtedly heavy the burden of the government, and also get unfavorable results.

(3) There is no clear line between the project owners and administrative departments on the clarification of “power, responsibility, and interest”. The post-quake restoration and reconstruction involves complicated relations among power, responsibility, and interest, which are unclear under current management mode. The shift of responsibilities is prone to happen. It goes against the orderly implementation of post-quake urban housing reconstruction.

(4) Insufficient participation of social assistance. Although the central government initiated the supporting partnership policy, under the current management mode, the participation from social communities is not strong enough to support the fast reconstruction in quake-affected areas.

(5) The lack of effective supervision causes corruption. Under the present post-quake urban housing reconstruction project management mode, the project legal person and the project owners are the two main bodies but devoid. The governmental administrative functional departments concentrate various powers, and directly authorized administrative departments to take charge of planning, investment, project supervision, delivery and acceptance, and housing allocation. The government to some extent is the “athlete” and the “referee”. When powers are over-concentrated, it is easy to breed corruption.

## 3 The optimization of the project management mode of post-quake restoration and reconstruction of housing for urban residents

### 3.1 The principles for the optimization of the project management mode of post-quake restoration and reconstruction of housing for urban residents

(1) The principle of integration management. The project management for post-quake urban housing reconstruction is an integration management mode for the whole project that takes the project legal entity as the main body. Meanwhile, it must bring the project organization items of the owner and contractors into the project management setup, ensuring the consistency of the economical interests of all the participants and the general interests of the project legal entity.

(2) The principle of professional management. It is not enough to merely take the integration management into consideration in the project management mode of post-quake urban housing reconstruction. It must fit in with the principle of professional management. The reason is that the owner usually lacks the experiences and ability for project management and it is hard for the owner to meet the requirements of professional management.

(3) The principle of clarifying duties, powers and interests. There are problems as the disappearance of the main body of the project and loose supervision and management in the current project management mode of post-quake urban housing reconstruction. It is vital that the management mode must follow the principle of separating the powers of the owner, contractor and constructor.

### 3.2 The optimized structure of the project management of post-quake urban housing reconstruction

Considering the problems in, and the principles for optimizing the project management mode of post-quake urban housing reconstruction, the optimized project management mode of post-quake urban housing reconstruction (shortened as “the optimized mode”) can be allocated into two different modes as “general construction contractor” and “general construction agent”. Furthermore, the “general construction agent” mode can be allocated into “general construction agent mode I” and “general construction agent mode II”

3.2.1 The optimized structure for general construction contractor mode

The general construction contractor mode is suitable for the in-situ reconstruction, reconstruction and development, and ex-situ reconstruction. In this mode, the leadership group of reconstruction work of housing for urban residents in municipal (or county) level signs contract with a general contractor, entrust them with the responsibility for the designing, constructing and transferring the whole project. And the general contractor will sublet the project to different subcontractors according to the specific situation of the project. And a technical supervision and evaluation group, consists of fund-raising team, technical supervision and evaluation team and policy directing team will be the contact with the social supporters and provide technical consultancies to the leadership group of reconstruction work of housing for urban residents in municipal (or county) level. And the owner’s committee of the post-quake resident housing reconstruction project, as well as the municipal (or county) resident housing recovery and reconstruction group will carry out the supervision of the project. See Figure 3.

Notes:

1. Fund-raising team  2. Technical supervision and evaluation team  3. Policy directing ream

4. Subcontractor 1  5. Subcontractor 2  6. Subcontractor 3

Figure 3  The general construction contractor mode for In-situ reconstruction, 
      reconstruction and development, and Ex-situ reconstruction

3.2.2 The optimized structure for general construction agent mode I

The general construction agent mode II is suitable for in-situ reconstruction, reconstruction and development, and ex-situ reconstruction. The difference between this mode and general contractor mode is that in this mode, the owner's committee of the disaster affected residents reconstruction project entrusts a project agency with the responsibility of the operation and management for the whole project. The agency signs contract with project contractors for the construction of the project, and also carry out the supervision and management of the construction. The contractor plays the role of project constructor, managed by the project agency, and hand over the project according to the contract. Meanwhile, the technical supervision and evaluation group will supervise and manage the work of the project agency and contractor according to the planning goal of the municipal (or county) urban housing reconstruction leadership group. See Figure 4.

Notes:

1. Fund-raising team  2. Technical supervision and evaluation team  3. Policy directing Team

Figure 4  The general construction agent mode I for the In-situ reconstruction, 
        reconstruction and development, and Ex-situ reconstruction

3.2.3 The optimized structure for general construction agent mode II

The general construction agent mode II is suitable for post-quake policy-ensuring urban housing projects. Though it is an agent mode, the investor and supervisor is different from that of the projects as urban housing reinforcement, in-situ reconstruction and ex-situ reconstruction. The investor is a governmental investment company presented by the leadership group of reconstruction work of housing for urban residents in municipal (or county) level. The supervisor is government housing administration. The project agent and contractor are in fact the manager and constructor of the project. Thus, the governmental investment company, government housing administration and the project agent sign a joint contract, that the governmental invest company and the project agent are responsible for the project operation and hand over the low-cost apartment to the government housing administration, and the latter is responsible for inspection, acceptance and distribution. See Figure 5.

Notes:

1. Government investment company  2. Government housing administration  3. Fund-raising team

4. Technical supervision and evaluation team  5. Policy directing team

Figure 5  The general construction agent mode II for post-quake policy-ensuring 
    urban housing reconstruction orojects

### 3.3 The advantages of the optimized post-quake urban housing reconstruction project management mode

Through the optimizing of the current mode of the project management of post-quake urban housing restoration and reconstruction, we shifted the old post-quake urban housing reconstruction project management mode (shortened as “old mode”) structure and related logic relations. The advantages are as follows:

(1) Drastically shortened the construction period. The “optimized mode” cut off the management level of the “old mode”, and implements an “integrated management” system. In the “old mode”, the preliminary work (including project initiation and approval, FSR, EIA, as well as examination of the construction plan) would take 5-6 months. In the “optimized mode”, according to the practice of the Post-Quake Rural Resident Housing Reconstruction Project Management Mode (shortened as “rural housing mode”), it only takes 2-3 months. In the “old mode”, it usually takes 10-12 months from the beginning to the finishing of the construction, but it only takes 6-8 months in the “optimized mode”.

(2) Drastically reduce construction costs. In the current “optimized mode”, there are professional organizations and supervision units involved. According to the “rural housing mode”, construction costs can be reduced to 620 RMB/m2 in the “optimized mode”, which is 87% of the “original mode” 715 RMB/m2.

(3) Drastically improve construction quality. In the “original mode”, less importance are attached to the quality of reconstruction, making people unsatisfied with or even complaining the projects. The living environment cannot be effectively improved. But in the “original mode”, with the implementation of quality control system, the quality of construction can be managed effectively thus achieving a great progress in urban housing construction.

(4) Drastically enhance the power of supervision and administration. In the “original mode”, due to the lack of strong supervision and administration, corruption can easily occur. In the “optimized mode”, with the presence of project legal person and project user, the shift of the function of the government, and the establishment of related supervision and administration system, the power of supervision and administration is greatly enhanced.

## 4 The supporting mechanisms of the project management mode of post-quake restoration and reconstruction of housing for urban residents

It is not enough for having a good post-quake urban housing reconstruction project management mode. Supporting mechanisms matching the project management mode should be also established. It is an important content for the project management mode of post-quake urban housing reconstruction. Only by establishing perfect management supporting mechanisms, the project management mode of post-quake urban housing reconstruction can play a better role.

(1) To complete project inspecting and supervising mechanism and project process control of post-quake urban housing reconstruction. On one hand, post-quake housing urban housing reconstruction is a long and complex process that needs three years, five years or even ten years; on the other hand, the inspection and supervision on post-quake urban housing reconstruction project is different from other project management, because a lot of residents do not have such knowledge and experience. Its main function and task is to control every limited resources input in the implementation process of post-quake urban housing reconstruction to play a role completely. So it is very important to complete the inspecting and supervising mechanism and process control of post-quake urban housing reconstruction project.

(2) To complete relative policy and law for post-quake urban housing reconstruction project. Currently, there are various governmental polices about post-quake urban housing reconstruction, but policies on subsidies for post-quake urban housing reconstruction and financing for it is far from enough. Meanwhile the continuous completion of laws on post-quake urban housing reconstruction is necessary. The rights and obligations of construction and management main bodies at all levels should be regularized. All the reconstruction participants must behave in accordance with regulations and laws.

(3) To strengthen social evaluation of post-quake urban housing reconstruction, and to improve the input efficiency of it. We must introduce social evaluation mechanism, and welcome supervision from social communities. At the same time, we can entrust a third party to evaluate the implementation, anti-earthquake performance and persistence effect of post-quake urban housing reconstruction projects, in order to form up an evaluation mode which features the mutual promotion between internal self-discipline and social supervision.

(4) To improve the coordinating and cooperating mechanism of post-quake urban housing reconstruction. From the view of structure of the project management mode of post-quake urban housing reconstruction, there are many people or mechanisms, which take part in the post-quake urban housing reconstruction. A good coordinating and cooperating mechanism should be established among participants. This is of great importance for the successful implementation of post-quake urban housing reconstruction project. Only through the coordination and cooperation among all reconstruction participants, the goals on project progress, quality, and cost could be finally achieved.

(5) To strengthen the internal and external supervising mechanism of post-quake urban housing reconstruction. In the process of post-quake urban housing reconstruction, besides the strengthening in the double supervision function of financial and auditing departments, the supervising functions of National People’s Congress, CPPCC, discipline inspection, supervision, news media, and society intermediary agencies can give a full play to project supervision. The source, quantity, distribution, and use of funds and commodities of post-quake reconstruction should be publicized regularly, and also be traceably audited.

## 5 Conclusion

Sichuan Wenchuan devastating earthquake is the most intense, wide-affected, and destructive tremor ever happened since the foundation of the People’s Republic of China. Although we are unable to accurately forecast and prevent the disasters, we can draw experience and learn lessons from the cost of blood and life, direct post-disaster reconstruction by relying on our own wisdoms, and to minimize the losses of such catastrophe.

Aiming at the existing problems in current post-quake reconstruction such as the absence of project main bodies, the unclearness among power, responsibility, and interests, and the defectiveness in reconstruction project progress control system, considering the particularity of post-quake reconstruction project management from other common project management mode in project management environment, the source of project fund, and the policy-based characteristic, this thesis optimizes the current “Administrative Project Management Mode”, and sets up a new mode in “Post-quake Urban Housing Reconstruction Project Management ”. This mode is helpful not only in overcoming the problems that exist in “Administrative Project Management Mode”, but also in establishing a control and supervising mode which can coordinates the interests among all participants in post-quake urban housing reconstruction. It is the perfection and innovation to the project management ideology and mode, and of the greatest importance to provide valuable references to the establishment of post-quake reconstruction project management system.

The post-Wenchuan earthquake reconstruction work is only at its beginning, and there are a lot of issues worth research. Still we have a long way to go. Deep research in some proactive problems like the coordination mechanism of post-quake reconstruction project management mode, multi-projects management mode, and multi-projects resources allocation will be the follow-up work of this thesis.

##### References

[1]	Xu Jiu-ping, Lu Yi. Comprehensive Integration Mode of Post-Earthquake Housing Reconstruction System Project [J]. System Project Theory and Practice, 2008(7): 1-16 (in Chinese)

[2]	Gao Yong-xiang, Chi Hui, Xu Xin. Realistic Thinking of Introducing Project Management Mode in Post-Wenchuan Earthquake Housing Reconstruction Project [J]. Construction Supervision, 2008(10) (in Chinese)

[3]	Lu Zhen-heng. Earthquake Disaster of South of Hyogo County in Japan and Its Revelation [J]. Shanxi Earthquake, 1995(2): 48-60 (in Chinese)

[4]	Xu Fu-hai. Post-Earthquake Housing Reconstruction Mode in Pakistan [J]. Chinese Disaster Reduction, 2008(1): 36-37 (in Chinese)

[5]	Zhang Tao, He Chang-zheng. Post-Earthquake Non-business Government Investment Project Construction Mode Analysis [J]. Sichuan University Journal (Philosophy Society Science Edition), 2009(2):120-128 (in Chinese)

[6]	Liao Yun-fang, Yang Guo-dong. Thinking About Non-Governmental Organization Taking Part in Post-Earthquake Reconstruction Effectively [J]. Decision and Information, 2008(9):156-157 (in Chinese)

[7]	Xu Zhi-chu. Processing Relation between Reconstruction Main Parts in Post-Disaster Reconstruction Correctly [J]. Modern Economy, 2008(7): 26-27 (in Chinese)

[8]	Post-Disaster Reconstruction Textbook. Leader Decision Information, 2008(7): 68-95 (in Chinese)

Sichuan Provincial People’s Government.