# Managing Change in Public Administration
Keeping Organizational Change on Track to High Performance

1. Christina Kirsch  2.Warren Parry

ChangeTrack Research, Level 3 Grafton Bond Building, 201 Kent Street, Sydney NSW 2000 Australia

Abstract  In an increasingly globalized world and in a world that has to deal with climate change and the economic upheaval created by the Great Financial Crisis, organizational change is not optional for our public administration institutions. The transition into a more sustainable and economically viable model of public administration requires unprecedented changes in the way our organizations operate. In order to be able to manage these change processes successfully, managers need to know whether change is on track to delivering the intended benefits and what corrective actions to take if change is off track. Despite good intentions, change takes longer and costs more than planned. More often than not it fails to deliver promised improvements and performance gains. Based on ten years of research CTRE has identified the factors which drive successful change and improved performance. Developed from the practical application of these findings, ChangeTracking is a tool for navigating change to deliver high performance. Like a Global Positioning System (GPS), ChangeTracking positions groups on a change map so leaders can see where change is on track and where it is not. And it shows the required actions where course correction is needed. ChangeTracking takes the guesswork out of managing change, giving leaders the information they need to navigate with confidence. It provides a means to actively engage people in a positive way during the change process, focusing their efforts on the factors that really make a difference. ChangeTracking accelerates change and delivers sustainable improvements in business performance. This paper provides an introduction to the empirically derived ChangeTracking model, the Change Map, and its potential use as a modelling and predictive tool.

Key words  Organizational change, Agility, Organizational performance

## 1 Introduction

Public administration is currently faced with unprecedented challenges – globalization, the Great Financial Crisis and ensuing economic downturn, global warming and growing pressure to become more sustainable, reduce carbon emissions and resource consumption, all coupled with an increasingly tight labour market and resource challenges due to increasing demands for services and limited income from rates and fees. It is not just about “doing more with less”, but increasingly about doing things differently, as the definition and expectations of government institutions and public administration are changing(Borins, 2001; Boyne, 2003; Gasco, 2003; Fernandez, 2006; Kettl, 2000; Pollit & Bouckaert, 2000; Stillman, 1999). Public administration organizations, as much as their private counterparts, are forced to adapt to these changing contingencies. Yet, in an increasingly populated and globalized world the pace of change is accelerating and often there will be several change processes simultaneously, ranging from the implementation of new technologies to structural changes or new ways of working. Employees not only have to manage their involvement in the change process, but at the same time ensure that the day-to-day work is getting done. Unsurprisingly, empirical studies have shown that all too often change projects fail to achieve the intended objectives (Anton, Petouhoff, & Schwartz 2003, Burnes 2004; Robertson & Seneviratne, 1995).

Managers and consultants responsible for organizational change processes need to know whether change is on track to delivering the intended benefits. When change is off track, leaders need to know what corrective actions to take. Good navigation is vital to successful change and improved performance. However, most navigation is based on guesswork or simplistic measures that don’t show how change is progressing early enough in a project’s lifetime. Subsequently, leaders find out too late that change is off track—by which point it is difficult to know what steps are needed to get back on the right course. Despite good intentions, change takes longer and costs more than planned. More often than not it fails to deliver promised improvements and performance gains.

How to successfully steer the organization through the rough waters of organizational change has become the real challenge. Change is not only inevitable; it has become the only constant in our increasingly interconnected world.

## 2 The challenges of managing organizational change

Considering the accelerating environmental dynamics, the increasing pressure on our governmental institutions to adapt to changes in legislation, funding, customer expectations, and the continuous pressure to do more with less and do it better, the ability to manage change is a core organizational competence for administrative institutions at all levels of government (Dawson 2003; Dunphy et al. 2003; Kanter et al. 1997; Kotter 1996; Romanelli and Tushman 1994).

Yet, the empirical literature still points to a high failure rate for organizational change projects, somewhere between 50% and 80% or above (Anton, Petouhoff, and Schwartz 2003, Beer and Nohria 2000; Brodbeck 2002; Bryant 1998; Burnes 2004; Clarke 1999; Sauer and Cuthbertson 2003; Stickland 1998). Over the last 20 years there has been an ongoing debate about the most successful way to manage change (Beer and Nohria 2000; Dawson 2003; Kanter et al. 1992; Kotter 1996; Pettigrew 1990; Romanelli and Tushman 1994; Stace and Dunphy 2001; Stickland 1998; Stacey 2003; Wilson 1992). This is not surprising considering the increasing importance that organizational change is playing in a more and more globalized, connected economy under increasing resource constraints, and the obvious difficulties in successfully managing change in organizations and institutions. What is needed is clear empirical data-based evidence regarding the factors that impact on the success of organizational change in public administration, based on a systemic and integrated approach.

## 3 Drivers of successful change management—the changetracking model

In 1998, ChangeTracking Research (CTRE) commenced a major research project to determine which factors would need to be measured to evaluate if change projects are on track. Taking a data-centred approach to change management CTRE developed a survey that captures the major variables determining and impacting on organizational change projects. The questionnaire that is used to collect data from staff in organisations has been streamlined and refined in repeated statistical analyses, which included extensive factor analyses, cluster analyses and reliability estimates. A comprehensive benchmarking database has been built from the responses of over 111,544 individuals answering 50 questions of the ChangeTracking survey across a variety of industries, nationalities and languages. This ChangeTracking benchmarking database has been formed from a larger database of over 350,000 responses, and contains only cleaned and complete datasets from a mix of organizations, types of change, industries, hierarchical levels etc.

Over the course of the research CTRE has asked more than 1500 questions to develop the current 50 “core” questions used in the ChangeTracking survey. The ChangeTracking survey uses a 7 point Likert scale, asking respondents to what extent a certain item is present within the organization, ranging from “not at all” to “very high”. The objective is to capture perceptions and to separate those from value judgments.  Therefore questions and anchors of the Likert scales are voiced in ways that reduce the level of response bias and allow the respondent’s answer to refer as closely as possible to direct perception as opposed to value judgements. In developing the ChangeTracking model and survey, all aspects of change have been systematically analysed across various types of change, including growth, restructuring, cost reduction and the implementation of new technology. A full range of change dynamics were explored in relation to various factors, i.e. complexity of the change project, available resources, training etc. The items that were taken into account also covered an extensive range of “people factors”, ranging from feelings to communications, involvement, accountability, leadership, clarity of direction, management competencies and organization values. The questions were refined using Factor Analysis to determine the best indicators.  Extensive statistical analyses were conducted on an ongoing basis in order to empirically analyse the underlying factor structure of the data, which provided the foundation for the development of the ChangeTracking model (Figure 1). The purpose of the statistical analysis was to empirically derive a valid and reliable factor structure.

The Model includes two Performance Outcomes and a number of critical drivers, including two clusters of emotions experienced by the teams: Passion and Drive and Disturbance.

The performance outcome variables are:

Realizing Business Benefits and Improving Business Performance.

“Realising Business Benefits” is defined as the extent to which elements of the business case for change have been achieved or will be achieved. The survey measures the extent to which planned functionality and/or capability has been achieved and whether or not people see that business benefits have been realized.

“Improving Business Performance” is defined as the improvement, as opposed to a decline, in effectiveness, cost management and customer service in the organization. The performance questions measure whether or not performance increases or decreases in the day to day operations of the organization while change is taking place.

Figure 1  Dimensions and clusters of the changetracking survey

CTRE identified six critical drivers that moderate the impact of change on performance  – Turbulence, Resources, Aligned Direction, Change Leadership, Work Roles and Emotional Energy. These performance drivers are further refined into clusters, to provide a common language for effective communication.

“Turbulence” refers to the overall amount of change taking place, the pace and stage of the change process and includes information regarding the risks and roadblocks encountered on the way.

“Resources” encompass all resources that are at the behest of the change project. The factor contains two clusters:

(1) Skills and Capabilities: whether teams have the capabilities, skills and staff levels they need to meet their objectives, or are receiving the necessary training to close the gaps, and

(2) Systems and Processes: whether workgroups have the systems and processes needed to achieve their objectives.

“Aligned Direction” gives insights into answering this question by measuring two main factors:

• Vision and Direction: Peoples’ understanding and agreement with the vision;

• Communication: The amount and type of information that people receive about the changes

“Change Leadership” measures the strength and manner of how leaders engage with their people through different levels in the organization:

• Management Commitment: whether or not leaders and sponsors of change at the Business Unit level demonstrate support and commitment for change.

• Team Leadership: Skills of the direct supervisor to manage people and their performance and how valued team members feel.

“Work Roles” measures how work is structured and organized. It includes the scales:

• Involvement: How and to what degree people are involved in planning and implementing change.

• Accountability: Extent to which people are held accountable, have role clarity and clear, measurable targets.

“Emotional Energy” refers to the actual emotions experienced by the employees and encompasses several emotional factors that have been derived empirically (Kirsch, Parry & Peake 2010). These basic emotion categories are subsumed under two clusters: Passion & Drive and Disturbance.

## 4 Analysing complex non-linear processes — the changetracking map

The traditional way of analysing and optimizing organizations, especially during Taylorism and scientific management, was based on a mechanistic paradigm of the Newtonian era. The problem or object of the analysis is broken into its various components, which are analysed in isolation. Time-and-motion studies, therblings, lighting levels are all isolated characteristics of a rather complex systems. The Newtonian paradigm is based on the assumption of linear processes that are deterministic in nature. Yet, quite obviously organizations are complex systems, whose various parts are in constant exchange, inter-connected by complex feedback loops and coupled processes, continuously in flux and adapting to an ever-changing external environment.

This realization has led to the advent of the socio-technical systems approach and more recently Complex Adaptive Systems theories. Yet, as Burns (2005) pointed out, all too often, the notion of a Complex Adaptive System is merely used as a metaphor to describe an organization, but not as a way to analyse it. The nonlinear nature of systemic processes requires new methods for the analysis of complex organizational systems and processes.

In order to adequately analyse the complex datasets collected from hundreds of organizational change processes, an advanced mathematical method for the analysis of complex nonlinear interactions amongst large data sets-Self Organizing Maps — has been used. A Self-Organizing Map (SOM) is a type of artificial neural network based on the work of Teuvo Kohonen, and is sometimes called a Kohonen map (Kohonen, 2001). The SOM is trained using unsupervised learning to produce a low-dimensional representation of the input space of the training samples, called a map. The map seeks to preserve the topological properties of the input space. This makes SOM useful for visualizing low-dimensional views of high-dimensional data.

SOMs, like most artificial neural networks, use either a training mode or a mapping mode. In the training mode, the SOM creates the map using input data. It is a competitive learning process, also called vector quantization. The SOM forms a semantic map where similar samples are mapped close together and dissimilar samples are mapped apart. This allows the clustering of variables with similar characteristics, and the distinction of dissimilar variables. Locations or “regions” on the SOM represent specific patterns of relationships amongst data. Regions define different patterns of strength and weakness across the change terrain. Individual Cells represent a unique algorithm of response combinations. The map allows to track organizational change processes over time and to compare different departments, teams, hierarchical levels etc.

Figure 2 shows an example of an organization which had implemented a new IT system. Despite good intentions, the project had gone seriously off track and misguided change management was a big part of the problem. Three months after the “go-live” date, business unit costs were 15% over the project’s operational budget and there were 1000 manual overrides per day. Low morale and a lack of role clarity among key people only highlighted how far off track the organization was. Like many government agencies, the organization had been using an employee survey to measure communication and training prior to the go-live date. When results showed that communication and training were sufficient, the senior management team confidently cut the change-management budget. They believed they could save money, but in reality when they made this decision, they in fact committed to a course of action where the project ran over budget and over schedule, and its benefit realisation was delayed by about eight months. The key issues were that accountability and passion and drive—the key factors driving cost management and improved customer service—had dropped significantly throughout the organization. The ChangeTracking survey showed software problems, a slow roll out of upgrades and inaccuracy of the database was contributing to staff frustration and the delay in benefit realisation. It emerged that staff simply did not trust the new IT system. Training had focused on how to use the system and not on its role in the business. Management had failed to address staff fears and chosen  not to talk about the cost-saving aspects of the new system. Lack of information prompted the spread of rumours, which fuelled high fear levels.

Figure 2  Example of an organization on the change map

In order to address these problems managers made sure that the business case was clearly communicated so all staff knew what was in it for them. Additional training was provided so that staff could develop trust and confidence. Open discussion helped to reduce their fears. Teams were given greater autonomy, including, for the first time, accountability for managing budgets, for which they were set clear targets to reduce unit costs. Managers were also provided with training to build management skills. Business leaders—faced with evidence of poor use of resources, spiralling costs and declining customer-service standards—had to understand the cause of problems and actively demonstrate leadership. They developed a clear strategy and worked to ensure that all stakeholders viewed the business, its customers and the company vision in the same way. Conflicting priorities were resolved saving the company time, cost and energy. Six months later the project had managed to get closer to the intended performance targets, employee morale had greatly improved and the organization was on track to achieving the intended performance improvements.

## 5 Determinants of project success and organizational performance

In order to determine the impact that the various items have on organizational performance, three stepwise regressions for all critical drivers onto the three aspects of organizational performance – cost management, customer service, and effectiveness – was conducted and the models with the 10 strongest coefficients were used. The regression analysis reveals that quick remedial action, confidence in leadership, and passion are important drivers of Business Performance Improvements (Table 1) and are exerting considerable influence on Cost Management, Effectiveness, and Customer Service. The strongest impact on performance came from “quick remedial action” and “confidence and trust in company leadership”—yet, closely followed by “people in your team feeling passion”.

In order to analyse the impact of items onto the organizational change project and its success, stepwise regressions for all critical drivers onto “realization of intended benefits”, “confidence and trust in the success of the project” and the “quality of the current change management” was conducted and the models with the 10 strongest coefficients were used. The regression analysis reveals that Passion is an important driver of project success (Table 2) and is exerting considerable influence on Realizing Benefits (Std. Beta. .08; Std. Error .002), Trust in Success (Std. Beta. .11; Std. Error .003), and Current Change Management (Std. Beta. .06; Std. Error .003). The strongest impact on project performance and success came from “confidence and trust in company leadership”, “agreement with the vision”, and “quick remedial action” – followed by ‘people in your team feeling passion’

Table 1  Impact of changetracking items on performance improvements
(Stepwise regression; models with 10 coefficients; n = 111 544)

|  | Effectiveness |  |  |  | Cost Management |  |  |  | Customer Service |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Std.Beta |  | Std.Error |  | Std.Beta |  | Std.Error |  | Std.Beta |  | Std.Error |
| Quick remedial action | 0.169 |  | 0.004 |  | 0.156 |  | 0.004 |  | 0.172 |  | 0.004 |  |
| Confidence and trust in company leadership | 0.143 |  | 0.003 |  | 0.095 |  | 0.003 |  | 0.130 |  | 0.003 |  |
| People are feeling Passion | 0.123 |  | 0.003 |  | 0.068 |  | 0.002 |  | 0.127 |  | 0.003 |  |
| Team has adequate processes | 0.081 |  | 0.004 |  | 0.075 |  | 0.003 |  | 0.062 |  | 0.004 |  |
| Team has sufficient human resources | 0.068 |  | 0.003 |  | 0.064 |  | 0.003 |  | 0.097 |  | 0.003 |  |
| Involvement in planning and implementing change | 0.057 |  | 0.002 |  | 0.054 |  | 0.002 |  | 0.053 |  | 0.002 |  |
| Clear objectives and outcomes |  |  |  |  | 0.072 |  | 0.003 |  | 0.071 |  | 0.003 |  |
| Awareness for the need of change |  |  |  |  | 0.075 |  | 0.003 |  | 0.052 |  | 0.003 |  |
| Team has adequate systems | 0.056 |  | 0.003 |  |  |  |  |  | 0.060 |  | 0.003 |  |
| Leader provides support and systems | -0.083 |  | 0.004 |  |  |  |  |  | -0.036 |  | 0.003 |  |
| Info from Manager |  |  |  |  | 0.042 |  | 0.002 |  |  |  |  |  |
| Team has adequate skills & capabilities |  |  |  |  | 0.047 |  | 0.003 |  |  |  |  |  |
| Leader provides timne and resources | 0.059 |  | 0.004 |  |  |  |  |  |  |  |  |  |
| Confidence in Business Unit leadership team | 0.099 |  | 0.003 |  |  |  |  |  |  |  |  |  |
| R2/Adjusted R2 F | 0.349 5708.48*** |  | 0.349 |  | 0.266 3844.89*** |  | 0.265 |  | 0.333 5299.08*** |  | 0.333 |  |

Table 2  Impact of change tracking items on realization of benefits
(Stepwise regression; model with 10 coefficients)

|  | Realizing Benefits |  |  |  | Trust in Success |  |  |  | Current Change Management |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Std.Beta |  | Std.Error |  | Std.Beta |  | Std.Error |  | Std.Beta |  | Std.Error |
| Confidence and trust in company leadership | 0.242 |  | 0.003 |  | 0.242 |  | 0.003 |  | 0.089 |  | 0.003 |  |
| Agreement with the vision | 0.267 |  | 0.002 |  | 0.215 |  | 0.003 |  | 0.089 |  | 0.003 |  |
| Quick remedial action | 0.159 |  | 0.003 |  | 0.159 |  | 0.004 |  | 0.185 |  | 0.004 |  |
| People are feeling Passion | 0.082 |  | 0.002 |  | 0.107 |  | 0.003 |  | 0.062 |  | 0.003 |  |
| Leadership provides time and resources | 0.054 |  | 0.002 |  | 0.056 |  | 0.003 |  | 0.137 |  | 0.003 |  |
| Awareness for the need of change | 0.099 |  | 0.002 |  | 0.093 |  | 0.003 |  |  |  |  |  |
| Team has adequate systems | 0.061 |  | 0.002 |  | 0.055 |  | 0.003 |  |  |  |  |  |
| Amount of teamwork | -0.056 |  | 0.002 |  | -0.078 |  | 0.003 |  |  |  |  |  |
| Information from written sources | 0.047 |  | 0.002 |  |  |  |  |  | 0.047 |  | 0.002 |  |
| People are thinking of leaving | -0.040 |  | 0.002 |  |  |  |  |  |  |  |  |  |
| Involvement in planning and implementing change |  |  |  |  | 0.041 |  | 0.002 |  |  |  |  |  |
| Confidence in Business Unit leadership team |  |  |  |  | 0.048 |  | 0.003 |  | 0.136 |  | 0.003 |  |
| Team has sufficient human resources |  |  |  |  |  |  |  |  | 0.118 |  | 0.002 |  |
| Supervisor’s performance management skills |  |  |  |  |  |  |  |  | 0.066 |  | 0.002 |  |
| People feeling Fear |  |  |  |  |  |  |  |  | 0.045 |  | 0.002 |  |
| R2/Adjusted R2 F | 0.573 4269.31*** |  | 0.573 |  | 0.573 12356.18*** |  | 0.537 |  | 0.450 8689.06*** |  | 0.450 |  |

## 6 Conclusion

Change Tracking research established a comprehensive database from the responses of over 450,000 individuals in organisations across a variety of industries, nationalities and languages and managed to empirically determine the factors that need to be measured to determine if change projects are on track to ensuring that business benefits are delivered. The ChangeTracking survey covers all aspects of the change process, including performance, business benefits, level of turbulence, use of resources, vision and direction, communications, leadership, involvement, teamwork and emotional energy.

The SOM analysis could show that at comparable levels of performance there are various ‘regions’, which are characterized by different driver profiles and which will require very different actions and interventions in order to move the organization or change process towards improved performance. The SOM proves a valuable tool to adequately reflect the complex interactions between the various aspects of the socio-technical system undergoing change. A regression analysis showed the importance of “quick remedial action” as an important determinant of the organizations agility, or capability to successfully adapt and change. Other crucial aspects are trust in the leadership of the organization, passion, adequate resources in terms of processes and sufficient staff, and employees being involved in the planning and implementation of the changes.

The ChangeTracking data model, data structure, results and recommendations are not based on “guess work” or theoretical deductions, but are derived from actual data via complex non-linear mathematical models based on neural network technology. Based on ten years of research CTRE has identified the factors which drive successful change and improved performance. Developed from the practical application of these findings, ChangeTracking is a tool for navigating change to deliver high performance. Like a Global Positioning System (GPS), ChangeTracking positions groups on a change map so leaders can see where change is on track and where it is not. And it shows the required actions where course correction is needed.

ChangeTracking takes the guesswork out of managing change, giving leaders the information they need to navigate with confidence. It provides a means to actively engage people in a positive way during the change process, focusing their efforts on the factors that really make a difference.

It also provides a means to track the process and progression of change projects over time and analyse typical pathways of change processes. This allows the determination of adequate actions and interventions depending on the stage and phase of the change process. Further research on longitudinal analyses of change processes is needed. Additional studies comparing the different types of change—ranging from IT implementations to organizational restructure—are needed in order to determine differences and commonalities across change processes. Overall the ChangeTracking model and map provide an actionable and robust approach to help practitioners successfully manage change processes and a new model and approach to guide research and communicate empirical findings.

##### References

[1]	Anton, J., Petouhoff, N. L., & Schwartz, L. M. (2003). Integrating, People, Process and Technology. The Anton Press: Santa Maria

[2]	Beer, M. and Nohria, N. (eds) (2000). Breaking the Code of Change. Boston, MA: Harvard Business School Press

[3]	Borins, S. (2001). The Challenge of Innovating in Government. Washington, DC: IBM Center for the Business of Government

[4]	Boyne, G..A. (2003). Sources of Public Service Improvement: A Critical Review and Research Agenda. Journal of Public Administration Research and Theory 13: 367-94

[5] 	Brodbeck, P. W. (2002). Implications for organization design: teams as pockets of excellence. Team Performance Management: an International Journal, 8(1/2): 21-38

[6]	Bryant, A. (1998). Beyond BPR: confronting the organizational legacy. Management Decision, 36(1): 25-30

[7]	Burnes, B. (2004). Managing Change, 4th edition. Harlow: FT/Prentice Hall

[8]	Burnes, B. (2005). Complexity theories and organizational change, International Journal of Management Reviews, 7 (2):73-90

[9]	Clarke, M. (1999). Management development: a new role in social change. Management Decision, 37(10): 767-777

[10]	Dawson, P. (2003). Reshaping Change: a Processual Perspective. London: Routledge

[11]	Dunphy, D., Griffiths, A. and Benn, S. (2003). Organizational Change for Corporate  Sustainability. London: Routledge

[12]	Gascó, M. (2003). New Technologies and Institutional Change in Public Administration, Social Science Computer Review, 21(1): 6-14

[13]	Fernandez, S. (2006). Managing Successful Organizational Change in the Public Sector: An Agenda for Research and Practice, Public Administration, 66 (2)

[14]	Kanter, R.M., Stein, B.A. and Jick, T.D. (1992). The Challenge of Organizational Change. New York: Free Press

[15]	Kettl, D.F. (2000). The Global Public Management Revolution: A Report on the Transformation of Governance. Washington, DC: Brookings Institution Press

[16]	Kohonen, T. (2001). Self-Organizing Maps, 3rd edition. Berlin: Springer Kotter, J.P. (1996). Leading Change. Boston, MA: Harvard Business School Press

[17]	Pettigrew, A.M. (1990). Studying strategic choice and strategic change. Organizational Studies, 11(1): 6-11

[18]	Pollitt, C., & Bouckaert, G. (2000). Public Management Reform. Oxford: Oxford University Press

[19]	Robertson, P. J., and Seneviratne, S. J.. (1995). Outcomes of Planned Organizational Change in the Public Sector: A Meta-Analytic Comparison to the Private Sector. Public Administration Review 55: 547-58

[20]	Romanelli, E. and Tushman, M.L. (1994). Organizational transformation as punctuated equilibrium: an empirical test. Academy of Management Journal, 37(5): 1141-1166.

[21]	Sauer, C. & Cuthbertson, C. (2003), The State of IT Project Management in the UK 2002-2003. Templeton College: Oxford

[22]	Stace, D. and Dunphy, D. (2001). Beyond the Boundaries: Leading and Re-Creating the Successful Enterprise, 2nd edition. Sydney: McGraw-Hill

[23]	Stacey, R.D. (2003). Strategic Management and Organisational Dynamics: The Challenge of Complexity. Harlow: FT/Prentice Hall

[24]	Stickland, F. (1998). The Dynamics of Change: Insights into Organisational Transition from the Natural World. London: Routledge

[25]	Stillman, R. J. (1999). Preface to Public Administration: A Search for Themes and Direction. 2nd ed. Burke, VA: Chatelaine Press

[26]	Wilson, D.C. (1992). A Strategy of Change. London: Routledge